## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibkalinagar W/S Scheme inclu | SM/07399 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Shibkalinagar Water Supply Scheme including one year Operation & Maintenance and repairing of distribution main, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001374/2020-2021 | 5130/AD | 08/02/2021 | 08/02/2022 | SUPER SKILL | 87.04 | 18.63 | 21.4 | 95
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibkalinagar W/S Scheme inclu | SM/07399 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000279/2023-2024 | 3078/AD | 28/09/2023 | 28/09/2023 | Resource Division | 0.3 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibkalinagar W/S Scheme inclu | SM/07399 | Retrofitting | Making and fixing of permanent display board at headwork site of Bhubannagar, Gobindarampur, Laxmipur, Madhusudanpur, Ramtanunagar, Shibkalinagar PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002142/2023-2024 | 942/KSD | 19/12/2023 | 24/12/2023 | BIMALENDU GIRI | 0.94 | 0.16 | 16.66 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibkalinagar W/S Scheme inclu | SM/07399 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000835/2023-2024 | 680/AD | 30/01/2024 | 30/01/2024 | Resource Division | 9.59 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibkalinagar W/S Scheme inclu | SM/07399 | Retrofitting | Repairing of Pump House and Boundary at 2nd Tubewell site of Shibkalinagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/07399) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002192/2024-2025 | 2073/KSD | 28/12/2024 | 17/01/2025 | M/S IDEAL WORKS | 1.64 | 0 | 0 | 90
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibkalinagar W/S Scheme inclu | SM/07399 | Retrofitting | Repairing of Pump House and Boundary at 1st Tubewell site of Shibkalinagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/07399) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002191/2024-2025 | 2072/KSD | 28/12/2024 | 17/01/2025 | LASKAR ENTERPRISE | 2.31 | 0 | 0 | 90
Total | [13 empty] | 101.83 | 18.79 | 18.45