## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-X, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/07401 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Nandakumarpur (Zone-I) Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer,HQ-I |  | ORD/001333/2020-2021 | 2222/AD | 08/10/2020 | 08/10/2021 | SUKALPA NIRMAN | 70.74 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-X, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/07401 | Retrofitting | Day to day annual operation and maintenance of Over Head Reservoir, rising main & Distribution System (CI/DI/AC/UPVC of pipeline) of Nandakumarpur (Zone - I) W/S Scheme under Raidighi Sub-Division of Alipore Division P.H.E. Dte. [From 15.12.2021 to 14.12.2022] | Assistant Engineer, Raidighi sub division |  | ORD/001187/2021-2022 | 557/RSD | 14/12/2021 | 14/12/2022 | M/S A.R. CONSTRUCTION | 4.47 | 0 | 0 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-X, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/07401 | Retrofitting | Extension distribution system (at Node no. 11) in Zone-X of Mathurapur - II Block under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/000245/2022-2023 | 78/RSD | 18/05/2022 | 17/07/2022 | BANGA NIRMAN | 4.81 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-X, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/07401 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Nandakumarpur (Zone-III) Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Raidighi sub division |  | ORD/001336/2020-2021 | 2220/AD | 08/10/2020 | 08/10/2021 | UNITED BUILDERS | 108.61 | 18.44 | 16.98 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-X, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/07401 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Kailaspur at Habitation - Bhuiner Gheri (Part-A) in Nandakumarpur - II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001234/2020-2021 | 566/RSD | 30/12/2020 | 28/02/2021 | M/S B.M. CONSTRUCTION | 4.47 | 4.47 | 99.86 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-X, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/07401 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Kailaspur at Habitation - Janar Gheri (Part-A) in Nandakumarpur - II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001236/2020-2021 | 568/RSD | 30/12/2020 | 28/02/2021 | M/S B.M. CONSTRUCTION | 4.48 | 4.47 | 99.91 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-X, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/07401 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Kailaspur at Habitation - Manager Gheri (Part-A) in Nandakumarpur - II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001237/2020-2021 | 569/RSD | 30/12/2020 | 28/02/2021 | M/S. M.M. ENTERPRISE | 4.51 | 4.51 | 99.86 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-X, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/07401 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Kailaspur at Habitation - Manger Gheri Purba (Part-A) in Nandakumarpur - II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001238/2020-2021 | 570/RSD | 30/12/2020 | 28/02/2021 | M/S. M.M. ENTERPRISE | 4.47 | 4.3 | 96.18 | 0
Total | [13 empty] | 206.57 | 36.19 | 17.52