## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Kusumtala W/S Scheme includ | SM/07402 | Retrofitting | Surging and repairing of 1st Tube well of Kusumtala Water Supply Scheme under JJM, Block - Namkhana under Kakdwip Sub-Division under Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000597/2022-2023 | 5922/AD | 19/10/2022 | 03/11/2022 | S.K.GOLUI | 5.1 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Kusumtala W/S Scheme includ | SM/07402 | Retrofitting | Relaying of damaged distribution System by new for Providing Functional Household Tap Connection (FHTC) to the remaining households in connection with Jal Swapna for Kusumtala Water Supply Scheme, Block - Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000466/2021-2022 | 2414/AD | 15/09/2021 | 30/10/2021 | PIJUSH KANTI TRIPATHI | 13.41 | 13.37 | 99.7 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Kusumtala W/S Scheme includ | SM/07402 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households and operation & maintenance for 1(One) year and repairing of distribution main of Kusumtala Water Supply Scheme, Block - Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001373/2020-2021 | 5129/AD | 08/02/2021 | 08/02/2022 | PIJUSH KANTI TRIPATHI | 73.47 | 105.66 | 143.83 | 100
Total | [13 empty] | 91.98 | 119.03 | 129.42