## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 2 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhablat W/S Scheme including on | SM/07403 | Retrofitting | Laying Rising Main 150 mm dia. D.I. (K9) pipe and inter connection between 1 & 2 for Dhablat W/S Scheme, Block - Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001930/2020-2021 | 1343/KSD | 23/02/2021 | 05/03/2021 | UNITED BUILDERS | 3.32 | 0 | 0 | 90
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 2 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhablat W/S Scheme including on | SM/07403 | Retrofitting | Supply of CIDF Sluice Valves and 150 mm dia. CIDF Pipes and Specials for laying rising main for Dhablat W/S Scheme, Block - Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001932/2020-2021 | 1345/KSD | 23/02/2021 | 05/03/2021 | NITYANANDA MONDAL | 3.68 | 0 | 0 | 90
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 2 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhablat W/S Scheme including on | SM/07403 | Retrofitting | Supply of 250 mm dia. CIDF pipe and sSpecials for laying rising main for Dhablat W/S Scheme, Block - Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001934/2020-2021 | 1347/KSD | 23/02/2021 | 05/03/2021 | UNITED BUILDERS | 4.71 | 0 | 0 | 90
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 2 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhablat W/S Scheme including on | SM/07403 | Retrofitting | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Golakpur (Part) of Dhablat W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000422/2020-2021 | 799/KSD | 15/10/2020 | 29/11/2020 | JAGANNATH ENTERPRISE | 3.35 | 0 | 0 | 98
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 2 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhablat W/S Scheme including on | SM/07403 | Retrofitting | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Prasadpur (Part) of Dhablat W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000440/2020-2021 | 826/KSD | 16/10/2020 | 30/11/2020 | M/S AMULLYA SARASWATI ENTERPRISE & CO. | 3.41 | 0 | 0 | 100
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 2 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhablat W/S Scheme including on | SM/07403 | Retrofitting | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Laxmibazar area (Part) of Dhablat W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000441/2020-2021 | 827/KSD | 16/10/2020 | 30/11/2020 | M/S SNEHALATA ENTERPRISE | 3.64 | 0 | 0 | 100
7 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 2 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhablat W/S Scheme including on | SM/07403 | Retrofitting | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Bamoner More area (Part) of Dhablat W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000472/2020-2021 | 1050/KSD | 19/12/2020 | 08/01/2021 | M/S SAKTI GIRI ENTERPRISE | 3.97 | 0 | 0 | 93
8 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 2 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhablat W/S Scheme including on | SM/07403 | Retrofitting | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Lalpur (Part) of Dhablat W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000421/2020-2021 | 798/KSD | 15/10/2020 | 29/11/2020 | DIPA CHHETRI | 3.11 | 3.02 | 97.34 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 2 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhablat W/S Scheme including on | SM/07403 | Retrofitting | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Basantapur (Part) of Dhablat W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000408/2020-2021 | 779/KSD | 14/10/2020 | 28/11/2020 | M/S. SONAMONI ENTERPRISE | 4.78 | 4.65 | 97.23 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 2 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhablat W/S Scheme including on | SM/07403 | Retrofitting | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Dhablat (Part) of Dhablat W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000409/2020-2021 | 780/KSD | 14/10/2020 | 28/11/2020 | M/S. SUNITY ENTERPRISE | 4.71 | 4.53 | 96.16 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 2 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhablat W/S Scheme including on | SM/07403 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000708/2023-2024 | 478/AD | 24/01/2024 | 24/01/2024 | Resource Division | 9.46 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 2 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhablat W/S Scheme including on | SM/07403 | Retrofitting | Laying distribution system for additional works Augmentation of Dhablat (Zone-I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-B) (SM/13876) (SM/07403) (SM/07405) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001332/2024-2025 | 5416/AD | 24/12/2024 | 18/04/2026 | MONDAL ENTERPRISE (MURSHIDABAD) | 44 | 0 | 0 | 51
Total | [13 empty] | 92.15 | 12.2 | 13.24