## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 7 (seven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Rajnagar W/S Scheme including | SM/07404 | Retrofitting | Construction of Rising Main, Platform, Road Restoration and Y junction for Augmentation of Rajnagar W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13875) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000406/2024-2025 | 3189/AD | 31/07/2024 | 29/09/2024 | UCON (II) | 45.01 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 7 (seven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Rajnagar W/S Scheme including | SM/07404 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the remaining households of Habitation: Pulaha and Pulastha of Rajnagar W/S Scheme, Block - Namkhana, under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000453/2020-2021 | 841/KSD | 16/10/2020 | 30/11/2020 | ASHIS ENTERPRISE | 4.67 | 3.43 | 73.55 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 7 (seven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Rajnagar W/S Scheme including | SM/07404 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the remaining households of Habitation: Angira and Atri of Rajnagar W/S Scheme, Block - Namkhana, under Kakdwip Sub Division of Alipore Division, P.H.E. Dte.(Part-1) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000461/2020-2021 | 851/KSD | 16/10/2020 | 30/11/2020 | ASHIS ENTERPRISE | 4.69 | 3.75 | 79.91 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 7 (seven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Rajnagar W/S Scheme including | SM/07404 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000799/2023-2024 | 644/AD | 30/01/2024 | 30/01/2024 | Resource Division | 7.78 | 0 | 0 | 0
Total | [13 empty] | 62.15 | 7.18 | 11.56