## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 2 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhablat W/S Scheme including on | SM/07405 | Retrofitting | Laying distribution system for additional works Augmentation of Dhablat (Zone-I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-B) (SM/13876) (SM/07403) (SM/07405) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001332/2024-2025 | 5416/AD | 24/12/2024 | 17/06/2026 | MONDAL ENTERPRISE (MURSHIDABAD) | 44 | 0 | 0 | 51
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 2 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhablat W/S Scheme including on | SM/07405 | Retrofitting | Laying distribution system, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main, FHTC after completion of FHTC work for 01 Year for Augmentation of Dhablat (Zone- I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000402/2023-2024 | 1901/AD | 01/08/2023 | 30/09/2023 | SUDIP PRADHAN | 62.64 | 0 | 0 | 85
Total | [13 empty] | 106.65 | 0 | 0