## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 9 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ramtanunagar W/S Scheme includ | SM/07408 | Retrofitting | Laying of UPVC pipe line for FHTC work of Ramtanunagar W/S Scheme, Block - Kakdwip under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000902/2021-2022 | 762/KSD | 29/11/2021 | 29/12/2021 | SARADA CONSTRUCTION | 4.58 | 4.55 | 99.43 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 9 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ramtanunagar W/S Scheme includ | SM/07408 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation: Majherpara, Laskarpara and others of Ramtanunagar W/S Scheme, Block - Kakdwip, under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. (PART-III) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000209/2020-2021 | 644/KSD | 19/08/2020 | 03/09/2020 | SARADA CONSTRUCTION | 4.48 | 3.91 | 87.3 | 95
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 9 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ramtanunagar W/S Scheme includ | SM/07408 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation - Madhya Para and others of Ramtanunagar W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000452/2020-2021 | 838/KSD | 16/10/2020 | 30/11/2020 | FORTUNE ENGINEERING | 3.59 | 3.45 | 96.19 | 97
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 9 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ramtanunagar W/S Scheme includ | SM/07408 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation - Muslim Para and others of Ramtanunagar W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000454/2020-2021 | 842/KSD | 16/10/2020 | 30/11/2020 | SARADA CONSTRUCTION | 3.7 | 3.55 | 96.12 | 96
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 9 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ramtanunagar W/S Scheme includ | SM/07408 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation - Ramtanupara and others of Ramtanunagar W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000448/2020-2021 | 834/KSD | 16/10/2020 | 30/11/2020 | FORTUNE ENGINEERING | 4.45 | 4.27 | 96.01 | 96
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 9 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ramtanunagar W/S Scheme includ | SM/07408 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation: Paschimpara, Panupara and others of Ramtanunagar W/S Scheme, Block - Kakdwip, under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (PART-II) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000210/2020-2021 | 645/KSD | 19/08/2020 | 03/09/2020 | G.M. ENTERPRISE | 4.48 | 3.1 | 69.28 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 9 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ramtanunagar W/S Scheme includ | SM/07408 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation: Ramtanupara, Tulsitala and others of Ramtanunagar W/S Scheme, Block - Kakdwip, under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (PART-II) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000211/2020-2021 | 646/KSD | 19/08/2020 | 03/09/2020 | PIJUSH KANTI TRIPATHI | 4.48 | 3.57 | 79.74 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 9 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ramtanunagar W/S Scheme includ | SM/07408 | Retrofitting | Hiring of Diesel Car / Luxury Taxi for official use of the Assistant Engineer, Kakdwip Sub Division, P.H.E. Dte. for the period from 01.02.2023 to 31.07.2023 | Assistant Engineer, Kakdwip Sub Division |  | ORD/002176/2022-2023 | 652/KSD | 31/01/2023 | 31/07/2023 | PIKASU BOSE | 2.39 | 2.33 | 97.32 | 90
9 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 9 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ramtanunagar W/S Scheme includ | SM/07408 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000827/2023-2024 | 672/AD | 30/01/2024 | 30/01/2024 | Resource Division | 7.13 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 9 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ramtanunagar W/S Scheme includ | SM/07408 | Retrofitting | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Govt. Officials under Alipore Division, PHE Dte. for the period from 01.07.2024 to 30.06.2025 [Actually work order valid for the period from 01.10.2024 to 31.12.2024 - 3 months] | Assistant Engineer,HQ-II | Junior Engineer-1 | ORD/000985/2024-2025 | 4002/AD | 28/09/2024 | 28/12/2024 | PARBATI MONDAL | 1.2 | 1.09 | 90.8 | 75
11 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 9 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ramtanunagar W/S Scheme includ | SM/07408 | Retrofitting | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Govt. Officials under Alipore Division, PHE Dte. for the period from 01.07.2024 to 30.06.2025 [Actually work order valid for the period from 01.07.2024 to 30.09.2024 - 3 months] | Assistant Engineer,HQ-II | Junior Engineer-1 | ORD/000534/2024-2025 | 2523/AD | 18/06/2024 | 18/09/2024 | PARBATI MONDAL | 1.2 | 0.72 | 60.05 | 100
Total | [13 empty] | 41.67 | 30.55 | 73.31