## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Nagendraganj W/S Scheme inc | SM/07409 | Retrofitting | Preparation of DPR including estimate for Providing FHTC at Nagendraganj W/S Scheme (Phase-A), Dhaspara W/S Scheme (Phase-A), Shibpur W/S Scheme (Phase-A) & Bishnupur W/S Scheme (Phase-A) W/S Scheme & it's adjacent areas, Block - Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. [W/O No. 518/KSD, 24.08.21, T.No. 1792/AD, 21-22] |  |  | VCH/002607/2021-2022 | BP-2021-22-510 | 22/03/2022 | 22/03/2022 | ROY CHOWDHURY ASSOCIATES | 4.7 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Nagendraganj W/S Scheme inc | SM/07409 | Retrofitting | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Chokirdar Para & Bar Para of Nagendraganj W/S Scheme, Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000416/2020-2021 | 792/KSD | 15/10/2020 | 29/11/2020 | M/S. BRINDABAN DAS & SONS | 3.34 | 3.16 | 94.7 | 95
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Nagendraganj W/S Scheme inc | SM/07409 | Retrofitting | Relaying UPVC Pipe Line for Retrofitting of FHTC from Node Point 11 to 104, 20 to 21, 21 to 23 & 20 to 42 of Nagendraganj W/S Scheme under Kakdwip Sub -Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000470/2020-2021 | 1048/KSD | 19/12/2020 | 08/01/2021 | M/S. JOYGURU ENTERPRISE | 4.45 | 4.41 | 99.07 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Nagendraganj W/S Scheme inc | SM/07409 | Retrofitting | Relaying UPVC Pipe Line for Retrofitting of FHTC from Node Point 245 to 246, 245 to 250, 254 to 255 & 255 to 256 of Nagendraganj W/S Scheme under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000431/2020-2021 | 817/KSD | 16/10/2020 | 30/11/2020 | M/S MODINA ENTERPRISE | 4.59 | 0 | 0 | 80
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Nagendraganj W/S Scheme inc | SM/07409 | Retrofitting | Relaying UPVC Pipe Line for Retrofitting of FHTC from Node Point 256 to 258, 258 to 259, 259 to 260 260 to 261, 261 to 262, 262 to 263 & 263 to 264 of Nagendraganj W/S Scheme under Kakdwip Sub -Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000432/2020-2021 | 818/KSD | 16/10/2020 | 30/11/2020 | SUDIP PRADHAN | 3.42 | 3.41 | 99.68 | 100
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Nagendraganj W/S Scheme inc | SM/07409 | Retrofitting | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Nagendraganj (Part) & Gobindapur (Part) of Nagendraganj W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000415/2020-2021 | 791/KSD | 15/10/2020 | 29/11/2020 | JOY ENGINEERING & CONSTRUCTION | 3.74 | 2.92 | 78.07 | 80
7 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Nagendraganj W/S Scheme inc | SM/07409 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000332/2023-2024 | 3147/AD | 29/09/2023 | 29/09/2023 | Resource Division | 0.3 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Nagendraganj W/S Scheme inc | SM/07409 | Retrofitting | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Nagendraganj Patra Para & Debimathurapur (Part) of Nagendraganj W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000414/2020-2021 | 790/KSD | 15/10/2020 | 29/11/2020 | M/S KALIPADA JANA | 3.18 | 5.9 | 185.54 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Nagendraganj W/S Scheme inc | SM/07409 | Retrofitting | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Nagendraganj Majhi para, Mondal para of Nagendraganj W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000398/2020-2021 | 771/KSD | 14/10/2020 | 28/11/2020 | BHUNIA BUILDERS | 2.92 | 2.84 | 97.34 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Nagendraganj W/S Scheme inc | SM/07409 | Retrofitting | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Nagendraganj (part), Debimathurapur (part) and Barui Para of Nagendraganj W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000399/2020-2021 | 772/KSD | 14/10/2020 | 28/11/2020 | M/S MODINA ENTERPRISE | 4.79 | 9.54 | 198.97 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Nagendraganj W/S Scheme inc | SM/07409 | Retrofitting | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Nagendraganj(part), Jana Para, Khan Para and Gobindapur(Part) of Nagendraganj W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000402/2020-2021 | 773/KSD | 14/10/2020 | 28/11/2020 | KHOKAN MONDAL | 4.78 | 9.49 | 198.58 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Nagendraganj W/S Scheme inc | SM/07409 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000701/2023-2024 | 471/AD | 24/01/2024 | 24/01/2024 | Resource Division | 5.71 | 0 | 0 | 0
Total | [13 empty] | 45.92 | 41.67 | 90.74