## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 3 (three) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibpur W/S Scheme including | SM/07413 | Retrofitting | Relaying UPVC Pipe Line for Retrofitting of FHTC at Madhya Para (Part) of Shibpur W/S Scheme, Block - Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000468/2020-2021 | 1046/KSD | 19/12/2020 | 08/01/2021 | SUDIP KHANRA | 3.16 | 3.16 | 99.83 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 3 (three) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibpur W/S Scheme including | SM/07413 | Retrofitting | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Dakshin Paschim Para (Part) of Shibpur W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000419/2020-2021 | 796/KSD | 15/10/2020 | 29/11/2020 | A.S.A.CONSTRUCTION AND CONSULTANT | 3.86 | 3.22 | 83.4 | 90
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 3 (three) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibpur W/S Scheme including | SM/07413 | Retrofitting | Relaying UPVC Pipe Line for Retrofitting of FHTC at Uttar Paschim Para (Part) of Shibpur W/S Scheme, Block - Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000439/2020-2021 | 825/KSD | 16/10/2020 | 30/11/2020 | ANANDA MAITY | 2.97 | 5.86 | 197.06 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 3 (three) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibpur W/S Scheme including | SM/07413 | Retrofitting | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Uttar Paschim Para (Part) of Shibpur W/S Scheme, Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000438/2020-2021 | 824/KSD | 16/10/2020 | 30/11/2020 | M/S. MOYNA ENTERPRISE | 2.72 | 2.66 | 97.81 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 3 (three) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibpur W/S Scheme including | SM/07413 | Retrofitting | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Madhya Para (Part) of Shibpur W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. (2nd Call) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000501/2020-2021 | 1074/KSD | 19/12/2020 | 08/01/2021 | M/S. PARAMESWAR ENTERPRISE | 4.74 | 9.06 | 191.37 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 3 (three) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibpur W/S Scheme including | SM/07413 | Retrofitting | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Uttar Purba Para (Part) of Shibpur W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000407/2020-2021 | 778/KSD | 14/10/2020 | 28/11/2020 | M/S KHAJABABA ENTERPRISE | 4.77 | 9.06 | 190.06 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 3 (three) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibpur W/S Scheme including | SM/07413 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000709/2023-2024 | 479/AD | 24/01/2024 | 24/01/2024 | Resource Division | 12.17 | 0 | 0 | 0
Total | [13 empty] | 34.39 | 33.02 | 96.02