## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XIII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Schem | SM/07577 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Jogendra Nagar at Habitation - Jogendra Nagara (Part-A) in Ghatbakultala Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001229/2020-2021 | 564/RSD | 30/12/2020 | 28/02/2021 | SANKAR HALDER | 4.82 | 4.59 | 95.11 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XIII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Schem | SM/07577 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Chaplarkhop Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Raidighi sub division |  | ORD/000512/2020-2021 | 5127/AD | 08/02/2021 | 08/02/2022 | M/S. DAS BUILDERS | 53.21 | 32.28 | 60.66 | 96
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XIII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Schem | SM/07577 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Jogendra Nagar at Habitation - Jogendra Nagara (Part-B) in Ghatbakultala Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/002364/2020-2021 | 736/RSD | 12/02/2021 | 13/04/2021 | M.S. ENTERPRISE | 4.82 | 4.05 | 83.94 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XIII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Schem | SM/07577 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households of Mouza-Ghatbakultala at Habitation-Ghatbakultala (Part-D) in Ghatbakultala piped water supply scheme , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division |  | ORD/000558/2021-2022 | 492/RSD | 04/10/2021 | 03/12/2021 | M/S R.K.ENTERPRISE | 4.8 | 3.42 | 71.32 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XIII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Schem | SM/07577 | Retrofitting | Remodeling of pipeline at (Node point - 21-23,23-25,25-26,26-28,28-156,156-158,26-27,28-29,156-157,158-159,30-31,160-161,162-163,63-64) of Chaplarkhop W/S Scheme under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001035/2021-2022 | 539/RSD | 30/11/2021 | 29/01/2022 | SWASTIK ENTERPRISE (NEW) | 4.8 | 4.64 | 96.79 | 100
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XIII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Schem | SM/07577 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Ghatbakultala at Habitation - Ghat Bakul Tala (Part-C) in Ghatbakultala Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division |  | ORD/002363/2020-2021 | 735/RSD | 12/02/2021 | 13/04/2021 | SWASTIK ENTERPRISE (NEW) | 4.82 | 4 | 83.02 | 100
7 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XIII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Schem | SM/07577 | Retrofitting | Inter connection between OHR and Distrubtion system with supply of Specials, Laying HDPE pipe, Restoration at Zone - XIII water supply scheme of Mathurapur - II Block (Chaplarkhop PWSS) in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/002230/2023-2024 | 922/AD | 08/02/2024 | 09/03/2024 | SUKUMAR HALDAR | 7.81 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XIII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Schem | SM/07577 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000658/2023-2024 | 262/AD | 15/01/2024 | 15/01/2024 | Resource Division | 5.36 | 0 | 0 | 0
Total | [13 empty] | 90.44 | 52.98 | 58.58