## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XIII, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/07578 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Ghatbakultala at Habitation - Ghat Bakul Tala (Part-B) in Ghatbakultala Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division |  | ORD/002357/2020-2021 | 734/RSD | 12/02/2021 | 13/04/2021 | M/S. BISWAS CONSTRUCTION (II) | 4.82 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XIII, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/07578 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Ghatbakultala at Habitation - Ghat Bakul Tala (Part-A) in Ghatbakultala Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001307/2020-2021 | 562/RSD | 30/12/2020 | 28/02/2021 | M/S KALPANA CONSTRUCTION | 4.82 | 0 | 0 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XIII, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/07578 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households of Mouza-Ghatbakultala at Habitation-Ghatbakultala (Part-E) in Ghatbakultala piped water supply scheme , District South 24 Parganas, Block- Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte | Assistant Engineer, Raidighi sub division |  | ORD/000607/2021-2022 | 528/RSD | 18/11/2021 | 17/01/2022 | L.N. ENTERPRISE | 4.77 | 0 | 0 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XIII, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/07578 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households of Mouza-Ghatbakultala at Habitation-Ghatbakultala (Part-F) in Ghatbakultala piped water supply scheme , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001155/2021-2022 | 569/RSD | 15/12/2021 | 13/02/2022 | S.P. CONSTRUCTION (II) | 4.77 | 0 | 0 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XIII, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/07578 | Retrofitting | Extension of pipeline in connection with Functional Household Tap Connection (FHTC) at Ghatbakultala (Node No. 27-25-22-16-15-13) under Ghatbakultala water supply scheme ( Zone-XIII of Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001582/2021-2022 | 711/RSD | 02/03/2022 | 01/05/2022 | N.B.N CONSTRUCTION | 4.76 | 0 | 0 | 100
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XIII, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/07578 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households of Mouza-Ghatbakultala at Habitation-Ghatbakultala (Part-G) in Ghatbakultala piped water supply scheme , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001590/2021-2022 | 774/RSD | 28/03/2022 | 27/05/2022 | M/S KALIPADA JANA | 4.75 | 0 | 0 | 100
7 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XIII, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/07578 | Retrofitting | Restoration of distribution system of Ghatbakultala W/S scheme (near Ashokenagar-Jgendranagar) at Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/000635/2022-2023 | 96/RSD | 07/06/2022 | 07/07/2022 | R.G. ENTERPRISE (I) | 4.76 | 0 | 0 | 100
8 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XIII, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/07578 | Retrofitting | Restoration of distribution system near node no. 139 of Zone-XIII Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/000636/2022-2023 | 97/RSD | 07/06/2022 | 07/07/2022 | R.G. ENTERPRISE (I) | 4.75 | 0 | 0 | 100
9 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XIII, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/07578 | Retrofitting | Restoration of distribution system near jogendranagar more to provide FHTC at Ghatbakultala W/S scheme at Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/000637/2022-2023 | 98/RSD | 07/06/2022 | 07/07/2022 | R.G. ENTERPRISE (I) | 3.42 | 0 | 0 | 100
10 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XIII, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/07578 | Retrofitting | Extension of pipeline in connection with Functional Household Tap Connection (FHTC) at Ghatbakultala water supply scheme (Zone-XIII of Mathurapur-I block for Mega Surface water based water supply scheme for Falta- Mathurapur, District South 24 parganas) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001768/2021-2022 | 626/RSD | 29/12/2021 | 13/01/2022 | L.N. ENTERPRISE | 4.47 | 0 | 0 | 100
11 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XIII, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/07578 | Retrofitting | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to the households under Banshtala Baragheri mouza (JL No. 114) & partly Ghatbakultala mouza (JL No. 116) in Mathurapur-I block, Zone-XIII under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Mathurapur-II under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division |  | ORD/000391/2022-2023 | 4484/AD | 31/08/2022 | 30/09/2022 | M/S. L.P. CONSTRUCTION | 28.94 | 0 | 0 | 100
12 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XIII, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/07578 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households of Mouza-Ghatbakultala at Habitation-Ghatbakultala (Part-D) in Ghatbakultala piped water supply scheme , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division |  | ORD/000558/2021-2022 | 492/RSD | 04/10/2021 | 03/12/2021 | M/S R.K.ENTERPRISE | 4.8 | 0 | 0 | 100
13 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XIII, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/07578 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000024/2021-2022 | 5661/AD | 27/01/2022 | 27/01/2022 | Resource Division | 0.7 | 0 | 0 | 0
Total | [13 empty] | 80.53 | 0 | 0