## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 5 (five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chandipur W/S Scheme including | SM/07580 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Chandipur Water Supply Scheme, Block - Kakdwip South 24 Pgs. District under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000495/2020-2021 | 5311/AD | 18/02/2021 | 18/02/2022 | TAPAN KUMAR BARIK | 79.87 | 35.88 | 44.93 | 75
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 5 (five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chandipur W/S Scheme including | SM/07580 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000832/2023-2024 | 677/AD | 30/01/2024 | 30/01/2024 | Resource Division | 5.35 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 5 (five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chandipur W/S Scheme including | SM/07580 | Retrofitting | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households along with construction of 01 no. Pump House including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Chandipur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001421/2023-2024 | 4601/AD | 14/12/2023 | 30/03/2025 | MAA BHABANI CONSTRUCTION (DUM DUM) | 47.31 | 0 | 0 | 70
Total | [13 empty] | 132.53 | 35.88 | 27.08