## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 8 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhaspara W/S Scheme including | SM/07581 | Retrofitting | Relaying UPVC Pipe Line for Retrofitting of FHTC from Node Point 256 to 257 (Part), 253 to 264, 264 to 265, 265 to 267, 211 to 223, 221 to 222, 41 to 42 (Part) & 42 to 43 (Part) of Dhaspara W/S Scheme under Kakdwip Sub -Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000436/2020-2021 | 822/KSD | 16/10/2020 | 30/11/2020 | G.M. ENTERPRISE | 4.78 | 4.78 | 100 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 8 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhaspara W/S Scheme including | SM/07581 | Retrofitting | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Panchayet Bazar Para (Part) of Dhaspara W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000417/2020-2021 | 794/KSD | 15/10/2020 | 29/11/2020 | M/S BHUNIA ENTERPRISE | 4.06 | 3.98 | 98.09 | 99
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 8 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhaspara W/S Scheme including | SM/07581 | Retrofitting | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Das Para, Muntan Para (Part) of Dhaspara W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000433/2020-2021 | 819/KSD | 16/10/2020 | 30/11/2020 | SUMAN INDUSTRIES PVT. LTD. | 4.35 | 2.7 | 62.04 | 90
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 8 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhaspara W/S Scheme including | SM/07581 | Retrofitting | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Master Para (Part) & Mali Para of Dhaspara W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000403/2020-2021 | 774/KSD | 14/10/2020 | 28/11/2020 | M/S. SIKHA ENTERPRISE | 4.77 | 9.35 | 196.08 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 8 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhaspara W/S Scheme including | SM/07581 | Retrofitting | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Dhaspara (Part) of Dhaspara W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000405/2020-2021 | 776/KSD | 14/10/2020 | 28/11/2020 | AVIJIT MAITY | 2.97 | 5.07 | 170.59 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 8 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhaspara W/S Scheme including | SM/07581 | Retrofitting | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Paschim Para (Part) of Dhaspara W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000536/2020-2021 | 793/KSD | 15/10/2020 | 29/11/2020 | SAB ENGINEERING WORKS | 3.83 | 3.71 | 97.04 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 8 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhaspara W/S Scheme including | SM/07581 | Retrofitting | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Mahendraganj (Part) & Ghol Para of Dhaspara W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000404/2020-2021 | 775/KSD | 14/10/2020 | 28/11/2020 | M/S. BABA KAPIL MUNI ENTERPRISE | 4.74 | 9.38 | 197.67 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 8 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhaspara W/S Scheme including | SM/07581 | Retrofitting | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Purba Para (Part) of Dhaspara W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000466/2020-2021 | 1044/KSD | 19/12/2020 | 08/01/2021 | M/S. JOYGURU ENTERPRISE | 3.52 | 6.91 | 196.11 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 8 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhaspara W/S Scheme including | SM/07581 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000703/2023-2024 | 473/AD | 24/01/2024 | 24/01/2024 | Resource Division | 12.79 | 0 | 0 | 0
Total | [13 empty] | 45.81 | 45.88 | 100.15