## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibpur W/S Scheme including on | SM/07582 | Retrofitting | Laying PUVC pipe line for providing Functional Household Tap Connection for Shibpur piped water supply Scheme, Block - Namkhana under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000482/2020-2021 | 1060/KSD | 19/12/2020 | 13/01/2021 | ASHIS ENTERPRISE | 4.72 | 4.5 | 95.24 | 96
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibpur W/S Scheme including on | SM/07582 | Retrofitting | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Shibpur Para (Part) of Shibpur W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000420/2020-2021 | 797/KSD | 15/10/2020 | 29/11/2020 | SUMAN INDUSTRIES PVT. LTD. | 4.09 | 4.08 | 99.91 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibpur W/S Scheme including on | SM/07582 | Retrofitting | Laying PUVC pipe line for providing Functional Household Tap Connection for Shibpur piped water supply Scheme, Block - Namkhana under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000477/2020-2021 | 1055/KSD | 19/12/2020 | 13/01/2021 | ANANTA KUMAR GIRI | 4.45 | 8.75 | 196.73 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibpur W/S Scheme including on | SM/07582 | Retrofitting | Restoration of Remaining Functional Household Tap Connection (FHTC) to the households of Habitation: Freserganj Dk Shibpur, Shibpur Uttar Majherpara and Uttar Paschim Shibpur of Shibpur W/S Scheme, Block - Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000459/2020-2021 | 848/KSD | 16/10/2020 | 30/11/2020 | ASHIS ENTERPRISE | 4.56 | 9.12 | 199.95 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibpur W/S Scheme including on | SM/07582 | Retrofitting | Laying PUVC pipe line for providing Functional Household Tap Connection for Shibpur piped water supply Scheme, Block - Namkhana under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000488/2020-2021 | 1065/KSD | 19/12/2020 | 13/01/2021 | GROWING CONCERN | 4.31 | 8.19 | 190.06 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibpur W/S Scheme including on | SM/07582 | Retrofitting | Restoration of Remaining Functional Household Tap Connection (FHTC) to the households of Habitation: Dk. Madhya Shibpur, Dk Paschim Shibpur and Uttar Purba Shibpur of Shibpur W/S Scheme, Block - Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000458/2020-2021 | 846/KSD | 16/10/2020 | 30/11/2020 | GROWING CONCERN | 4.37 | 8.74 | 199.81 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibpur W/S Scheme including on | SM/07582 | Retrofitting | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Dk. Madhya Shibpur and adjoining areas of Shibpur W/S Scheme, Block - Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000215/2020-2021 | 650/KSD | 19/08/2020 | 03/09/2020 | ANANTA KUMAR GIRI | 4.68 | 9.35 | 199.93 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibpur W/S Scheme including on | SM/07582 | Retrofitting | Laying of rising main & distribution main and retrofitting of FHTC under JJM for Shibpur Water Supply Scheme, Block - Namkhana under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000199/2022-2023 | 2685/AD | 30/06/2022 | 30/07/2022 | BIMALENDU GIRI | 19.72 | 19.66 | 99.72 | 100
9 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibpur W/S Scheme including on | SM/07582 | Retrofitting | Laying distribution system for Providing FHTC to all households for Augmentation of Sibpur (Zone-I and II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000987/2023-2024 | 3006/AD | 26/09/2023 | 26/10/2023 | PALCON | 11.99 | 1.42 | 11.82 | 100
10 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibpur W/S Scheme including on | SM/07582 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000797/2023-2024 | 642/AD | 30/01/2024 | 30/01/2024 | Resource Division | 8.54 | 0 | 0 | 0
Total | [13 empty] | 71.42 | 73.8 | 103.34