## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 5 (five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dwarikanagar W/S Scheme includ | SM/07586 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Dwariknagar Water Supply Scheme including one year Operation & Maintenance and repairing of distribution main, Block - Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001369/2020-2021 | 5367/AD | 19/02/2021 | 19/02/2022 | M/S. PROMILA CONSTRUCTION | 98.02 | 0 | 0 | 75
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 5 (five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dwarikanagar W/S Scheme includ | SM/07586 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000796/2023-2024 | 641/AD | 30/01/2024 | 30/01/2024 | Resource Division | 5.4 | 0 | 0 | 0
Total | [13 empty] | 103.42 | 0 | 0