## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 3 (three) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mahishamari W/S Scheme includ | SM/07587 | Retrofitting | Laying of UPVC pipe line by replacing the damaged pipe line of different dia. for providing FHTC at Mahishamari Water Supply Scheme, Block - Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000470/2021-2022 | 2418/AD | 15/09/2021 | 30/10/2021 | M. MUKHERJEE | 14.85 | 14.83 | 99.9 | 100
2 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 3 (three) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mahishamari W/S Scheme includ | SM/07587 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Mahishmari Water Supply Scheme, Block - Sagar, South 24 Parganas District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001243/2020-2021 | 2274/AD | 12/10/2020 | 12/10/2021 | M. MUKHERJEE | 106.14 | 17.05 | 16.07 | 95
3 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 3 (three) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mahishamari W/S Scheme includ | SM/07587 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000712/2023-2024 | 482/AD | 24/01/2024 |  | Resource Division | 6.62 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 3 (three) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mahishamari W/S Scheme includ | SM/07587 | Retrofitting | Laying distribution system for providing FHTC for Augmentation of Mahishamari (Zone - I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-A) (SM/13872) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000428/2024-2025 | 3258/AD | 06/08/2024 | 04/11/2024 | M. MUKHERJEE | 150.27 | 0 | 0 | 0
Total | [13 empty] | 277.87 | 31.88 | 11.47