## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Srinagar W/S Scheme including o | SM/07591 | Retrofitting | Laying of UPVC pipe line for providing FHTC damaged due to upgradation of Road for Srinagar Water Supply Scheme, Block - Kakdwip under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001551/2021-2022 | 6727/AD | 17/03/2022 | 01/04/2022 | SUDIP PRADHAN | 11.34 | 11.28 | 99.42 | 90
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Srinagar W/S Scheme including o | SM/07591 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000831/2023-2024 | 676/AD | 30/01/2024 | 30/01/2024 | Resource Division | 6.62 | 0 | 0 | 0
Total | [13 empty] | 17.97 | 11.28 | 62.77