## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Srinagar Water Supply Sche | SM/07592 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Srinagar Water Supply Scheme (Habitation- Sardarpara), Block - Canning-II, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - II) | Assistant Engineer, Canning sub division |  | ORD/000090/2022-2023 | 294/CSD | 20/05/2022 | 29/06/2022 | NATURAL RESOURCES CONSORTIUM | 4.84 | 0 | 0 | 87
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Srinagar Water Supply Sche | SM/07592 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Srinagar Water Supply Scheme, Block - Canning-II, South 24 Parganas District under Canning Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year | Assistant Engineer, Canning sub division |  | ORD/000085/2020-2021 | 5308/AD | 18/02/2021 | 18/02/2022 | NATURAL RESOURCES CONSORTIUM | 89.65 | 117.56 | 131.13 | 77
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Srinagar Water Supply Sche | SM/07592 | Retrofitting | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (500 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) for Srinagar Water Supply Scheme including one year Operation and Maintenance of scheme, Block - Canning-II South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001999/2022-2023 | 12813/AD | 16/03/2023 | 15/05/2023 | SAHANA ENTERPRISE | 52.81 | 4.54 | 8.59 | 99
Total | [13 empty] | 147.3 | 122.09 | 82.89