## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 20 (twenty) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Adhia Water Supply Sche | SM/07596 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Adhia Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Canning sub division |  | ORD/001306/2020-2021 | 2223/AD | 08/10/2020 | 08/10/2021 | M/S. MIHIR KUMAR NASKAR | 85.78 | 77.8 | 90.7 | 75
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 20 (twenty) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Adhia Water Supply Sche | SM/07596 | Retrofitting | Construction of 400 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing )with 20 mtr. staging height including foundation, pipeline connection and cost of pipes , specials etc. of Adhia piped water supply scheme of Canning-I Block under Canning Sub- Division of Alipore Division, PHE Dte. [SM/07596 & SM/15477] | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000690/2024-2025 | 4271/AD | 28/10/2024 | 25/07/2025 | MAMON ENTERPRISE AND CONSTRUCTION | 128.22 | 0 | 0 | 0
Total | [13 empty] | 213.99 | 77.8 | 36.36