## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 5 (five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Puinjali Water Supply Sche | SM/07597 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Puinjali Water Supply Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Canning sub division |  | ORD/000089/2020-2021 | 5124/AD | 08/02/2021 | 08/02/2022 | RAMEN GHOSH | 87.24 | 0 | 0 | 82
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 5 (five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Puinjali Water Supply Sche | SM/07597 | Retrofitting | Laying of pipeline of uncovered FHTC work area of Puinjali Water Supply Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001179/2022-2023 | 8775/AD | 21/12/2022 | 20/01/2023 | RAMEN GHOSH | 18.23 | 17.92 | 98.32 | 80
Total | [13 empty] | 105.47 | 17.92 | 16.99