## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 08 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bhaleya Water Supply Sch | SM/07598 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Bhaleya Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Canning sub division |  | ORD/001217/2020-2021 | 1619/AD | 28/08/2020 | 28/08/2021 | PUTUL RANI MAITY | 86.44 | 110.6 | 127.94 | 92
Total | [13 empty] | 86.44 | 110.6 | 127.94