## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 20 (twenty) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Srinarayanpur W/S Scheme in | SM/07626 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Srinarayanpur Water Supply Scheme including one year Operation & Maintenance and repairing of distribution main, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001349/2020-2021 | 5199/AD | 12/02/2021 | 12/02/2022 | M/S. JHARNA ENTERPRISE | 155.66 | 233.91 | 150.27 | 97
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 20 (twenty) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Srinarayanpur W/S Scheme in | SM/07626 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000770/2023-2024 | 604/AD | 29/01/2024 | 29/01/2024 | Resource Division | 18.94 | 0 | 0 | 0
Total | [13 empty] | 174.6 | 233.91 | 133.97