## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 04 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lot-126 Water Supply Sche | SM/07627 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Lot No. - 126 Water Supply Scheme Block - Basanti, South 24 Parganas District under Canning Sub Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of Scheme for 01 (one) year. | Assistant Engineer, Canning sub division |  | ORD/001375/2020-2021 | 5131/AD | 08/02/2021 | 08/02/2022 | K.P. CONSTRUCTION | 189.54 | 328.04 | 173.07 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 04 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lot-126 Water Supply Sche | SM/07627 | Retrofitting | Laying pipe line to connect the uncovered habitation of Lot No.-126 W/S Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000270/2022-2023 | 262/CSD | 19/05/2022 | 18/06/2022 | K.P. CONSTRUCTION | 4.8 | 4.72 | 98.33 | 99
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 04 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lot-126 Water Supply Sche | SM/07627 | Retrofitting | Inter connection and rising main with supply of specials at Augmentation of Lot No. 126 W/S Scheme (Zone-I and II), Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. [Part - B] | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/002016/2022-2023 | 12922/AD | 21/03/2023 | 20/05/2023 | S.P. CONSTRUCTION (I) | 97.64 | 1.71 | 1.75 | 80
Total | [13 empty] | 291.98 | 334.46 | 114.55