## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 15 (fifteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Daria Water Supply Sch | SM/07628 | Retrofitting | Relaying and repairing of pipeline Daria Water Supply Scheme near PH - 1, 2 and 3 Block-Canning -I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/000112/2021-2022 | 1195/AD | 07/07/2021 | 21/08/2021 | DEBARATI ENTERPRISE | 35.86 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 15 (fifteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Daria Water Supply Sch | SM/07628 | Retrofitting | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 15 (fifteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Daria Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Part B) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000015/2022-2023 | 332/AD | 18/04/2022 | 18/04/2023 | M/S. ROY CHOWDHURY & CO. | 110.99 | 0 | 0 | 68
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 15 (fifteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Daria Water Supply Sch | SM/07628 | Retrofitting | Repairing and extension of pipeline for FHTC work for Daria Waster Supply Scheme, Block-Canning -I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000197/2022-2023 | 2642/AD | 29/06/2022 | 29/07/2022 | A.K. SIKDAR | 16.14 | 0 | 0 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 15 (fifteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Daria Water Supply Sch | SM/07628 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000014/2021-2022 | 5620/AD | 25/01/2022 | 25/01/2022 | Resource Division | 5.4 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 15 (fifteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Daria Water Supply Sch | SM/07628 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000017/2022-2023 | 1174/AD | 27/05/2022 | 27/05/2022 | Resource Division | 3.98 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 15 (fifteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Daria Water Supply Sch | SM/07628 | Retrofitting | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 15 (fifteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Daria Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. [Part - A] | Assistant Engineer, Canning sub division |  | ORD/001136/2021-2022 | 5542/AD | 20/01/2022 | 20/01/2023 | A.K. SIKDAR | 47.45 | 0 | 0 | 100
Total | [13 empty] | 219.82 | 0 | 0