## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | SM/07629 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Uttar Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ IV) | Assistant Engineer, Canning sub division |  | ORD/001392/2020-2021 | 993/CSD | 13/11/2020 | 28/12/2020 | TITHI ENTERPRISE | 4.78 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | SM/07629 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ XII) | Assistant Engineer, Canning sub division |  | ORD/001527/2020-2021 | 1193/CSD | 15/12/2020 | 29/01/2021 | A.P.C.ENGINEERS CO-OPERATIVE SOCIETY LTD. | 4.65 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | SM/07629 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ IX) | Assistant Engineer, Canning sub division |  | ORD/001523/2020-2021 | 1191/CSD | 15/12/2020 | 29/01/2021 | DIPTI ENTERPRISE | 4.74 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | SM/07629 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VII) | Assistant Engineer, Canning sub division |  | ORD/001387/2020-2021 | 989/CSD | 13/11/2020 | 28/12/2020 | P.P. CONCERN | 4.66 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | SM/07629 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ XV) | Assistant Engineer, Canning sub division |  | ORD/001536/2020-2021 | 1195/CSD | 15/12/2020 | 29/01/2021 | R.G. ENTERPRISE (I) | 4.51 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | SM/07629 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ IV) | Assistant Engineer, Canning sub division |  | ORD/001193/2020-2021 | 986/CSD | 13/11/2020 | 28/12/2020 | SWASTIK CONSTRUCTION | 4.73 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | SM/07629 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ II) | Assistant Engineer, Canning sub division |  | ORD/001383/2020-2021 | 984/CSD | 13/11/2020 | 28/12/2020 | D.R.CONSTRUCTION | 4.62 | 0 | 0 | 100
8 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | SM/07629 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Uttar Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VIII) | Assistant Engineer, Canning sub division |  | ORD/001540/2020-2021 | 1199/CSD | 15/12/2020 | 29/01/2021 | TITHI ENTERPRISE | 4.7 | 0 | 0 | 100
9 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | SM/07629 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Uttar Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ IX) | Assistant Engineer, Canning sub division |  | ORD/001541/2020-2021 | 1200/CSD | 15/12/2020 | 29/01/2021 | PROTIVA CONSTRUCTION | 4.66 | 0 | 0 | 100
10 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | SM/07629 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ XIII) | Assistant Engineer, Canning sub division |  | ORD/001534/2020-2021 | 1194/CSD | 15/12/2020 | 29/01/2021 | M/S KALPANA CONSTRUCTION | 4.6 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | SM/07629 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Uttar Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ X) | Assistant Engineer, Canning sub division |  | ORD/001542/2020-2021 | 1201/CSD | 15/12/2020 | 29/01/2021 | PROTIVA CONSTRUCTION | 4.61 | 0 | 0 | 100
12 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | SM/07629 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ I) | Assistant Engineer, Canning sub division |  | ORD/001382/2020-2021 | 983/CSD | 13/11/2020 | 28/12/2020 | D.R.CONSTRUCTION | 4.71 | 4.7 | 99.76 | 100
13 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | SM/07629 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VI) | Assistant Engineer, Canning sub division |  | ORD/001386/2020-2021 | 988/CSD | 13/11/2020 | 28/12/2020 | NANDALAL DAS | 4.58 | 0 | 0 | 100
14 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | SM/07629 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Dakshin Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - III) | Assistant Engineer, Canning sub division |  | ORD/001435/2020-2021 | 963/CSD | 07/11/2020 | 22/12/2020 | TITHI ENTERPRISE | 4.69 | 0 | 0 | 100
15 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | SM/07629 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Garkhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ III) | Assistant Engineer, Canning sub division |  | ORD/001390/2020-2021 | 991/CSD | 13/11/2020 | 28/12/2020 | ARANYA ENTERPRISE | 4.78 | 0 | 0 | 100
16 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | SM/07629 | Retrofitting | roviding Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VIII) | Assistant Engineer, Canning sub division |  | ORD/001389/2020-2021 | 990/CSD | 13/11/2020 | 28/12/2020 | FIDERE MARINE SERVICES PVT. LTD. | 4.7 | 4.68 | 99.5 | 100
17 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | SM/07629 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Uttar Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - II) | Assistant Engineer, Canning sub division |  | ORD/001436/2020-2021 | 964/CSD | 07/11/2020 | 22/12/2020 | PROTIVA CONSTRUCTION | 4.71 | 0 | 0 | 100
18 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | SM/07629 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Uttar Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ V) | Assistant Engineer, Canning sub division |  | ORD/001427/2020-2021 | 994/CSD | 13/11/2020 | 28/12/2020 | PROTIVA CONSTRUCTION | 4.7 | 0 | 0 | 100
19 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | SM/07629 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Garkhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - II) | Assistant Engineer, Canning sub division |  | ORD/001428/2020-2021 | 961/CSD | 07/11/2020 | 22/12/2020 | ARANYA ENTERPRISE | 4.71 | 0 | 0 | 100
20 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | SM/07629 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Garkhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ IV) | Assistant Engineer, Canning sub division |  | ORD/001537/2020-2021 | 1196/CSD | 15/12/2020 | 29/01/2021 | ARANYA ENTERPRISE | 4.74 | 0 | 0 | 100
21 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | SM/07629 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Uttar Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VII) | Assistant Engineer, Canning sub division |  | ORD/001539/2020-2021 | 1198/CSD | 15/12/2020 | 29/01/2021 | PROTIVA CONSTRUCTION | 4.74 | 0 | 0 | 100
22 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | SM/07629 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ III) | Assistant Engineer, Canning sub division |  | ORD/001190/2020-2021 | 985/CSD | 13/11/2020 | 28/12/2020 | GOUTAM HALDAR (I) | 4.65 | 4.64 | 99.79 | 100
23 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | SM/07629 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Dakshin Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - II) | Assistant Engineer, Canning sub division |  | ORD/001433/2020-2021 | 962/CSD | 07/11/2020 | 22/12/2020 | TITHI ENTERPRISE | 4.7 | 0 | 0 | 100
24 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | SM/07629 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ X) | Assistant Engineer, Canning sub division |  | ORD/001406/2021-2022 | 813/CSD | 16/09/2021 | 31/10/2021 | SHARANYA CONSTRUCTION | 4.78 | 0 | 0 | 0
25 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | SM/07629 | Retrofitting | Sinking of 250mm x 150mm dia. 350 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. -4 of Dakshin Redokhali Water Supply Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000057/2022-2023 | 793/AD | 12/05/2022 | 11/06/2022 | BHATTACHARJEE AND CO. | 17.97 | 0 | 0 | 100
26 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | SM/07629 | Retrofitting | Repairing of pipe line and also additional pipe line is required to connect the uncovered habitations at Mouza-Herobhanga, Garkhali, Uttar Rendokhali for FHTC work of Dakshin Rendokhali Water Supply Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/001062/2021-2022 | 5297/AD | 04/01/2022 | 05/03/2022 | M/S CHANDIMATA CONSTRUCTION | 33.45 | 0 | 0 | 0
27 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | SM/07629 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Uttar Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - I) | Assistant Engineer, Canning sub division |  | ORD/000606/2020-2021 | 844/CSD | 12/10/2020 | 26/11/2020 | PROTIVA CONSTRUCTION | 4.74 | 0 | 0 | 100
28 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | SM/07629 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000149/2023-2024 | 840/AD | 27/05/2023 | 27/05/2023 | Resource Division | 1.72 | 0 | 0 | 0
29 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | SM/07629 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Dakshin Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - I) | Assistant Engineer, Canning sub division |  | ORD/000605/2020-2021 | 843/CSD | 12/10/2020 | 26/11/2020 | TITHI ENTERPRISE | 4.74 | 0 | 0 | 0
30 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | SM/07629 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ V) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001385/2020-2021 | 987/CSD | 13/11/2020 | 28/12/2020 | M/S P. B. CONSTRUCTION | 4.79 | 0 | 0 | 100
31 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | SM/07629 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Uttar Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VI) | Assistant Engineer, Canning sub division | Junior Engineer-2 | ORD/001538/2020-2021 | 1197/CSD | 15/12/2020 | 29/01/2021 | ARANYA ENTERPRISE | 4.79 | 0 | 0 | 100
32 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | SM/07629 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Uttar Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ III) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001391/2020-2021 | 992/CSD | 13/11/2020 | 28/12/2020 | TITHI ENTERPRISE | 4.72 | 0 | 0 | 100
33 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | SM/07629 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Garkhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - I) | Assistant Engineer, Canning sub division |  | ORD/000604/2020-2021 | 842/CSD | 12/10/2020 | 26/11/2020 | ARANYA ENTERPRISE | 4.74 | 0 | 0 | 0
34 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | SM/07629 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ XI) | Assistant Engineer, Canning sub division |  | ORD/001525/2020-2021 | 1192/CSD | 15/12/2020 | 29/01/2021 | DIPA CHHETRI | 4.71 | 0 | 0 | 95
35 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | SM/07629 | Retrofitting | Inter connection for TW No. -1 & 2 with reservoir at Dk. Redokhali W/S Scheme, Block- Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001609/2020-2021 | 1341/CSD | 04/01/2021 | 03/02/2021 | SUKANTA HALDER | 1.17 | 0 | 0 | 90
36 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | SM/07629 | Retrofitting | Relaying of pipeline due to construction of PMGSY road at Dakshin Redokhali W/S Scheme in connection with FHTC work, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (SM/07629) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001017/2023-2024 | 3302/AD | 07/10/2023 | 21/11/2023 | SAHANA ENTERPRISE | 41.61 | 0 | 0 | 90
37 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | SM/07629 | Retrofitting | Laying of additional pipe line and Protection of pipe line at Dakshin Redokhali W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002977/2024-2025 | 34./CSD | 09/01/2025 | 08/02/2025 | BHATTACHARYA ENTERPRISE | 4.63 | 0 | 0 | 0
Total | [13 empty] | 246.23 | 14.02 | 5.69