## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone-II) | SM/07630 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Baria of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VII) | Assistant Engineer, Canning sub division |  | ORD/001443/2020-2021 | 997/CSD | 13/11/2020 | 28/12/2020 | SUSHANTA MANDAL | 4.71 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone-II) | SM/07630 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Sachea Khali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VII) | Assistant Engineer, Canning sub division |  | ORD/001553/2020-2021 | 1208/CSD | 15/12/2020 | 29/01/2021 | KUNDU CONSTRUCTION CO. | 4.7 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone-II) | SM/07630 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Baria of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VIII) | Assistant Engineer, Canning sub division |  | ORD/001543/2020-2021 | 1202/CSD | 15/12/2020 | 29/01/2021 | SUKANTA HALDER | 4.78 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone-II) | SM/07630 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Sachea Khali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - II) | Assistant Engineer, Canning sub division |  | ORD/001454/2020-2021 | 1011/CSD | 13/11/2020 | 28/12/2020 | NAZRUL ENTERPRISE | 4.72 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone-II) | SM/07630 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Bugulakhali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - III) | Assistant Engineer, Canning sub division |  | ORD/001449/2020-2021 | 1009/CSD | 13/11/2020 | 28/12/2020 | SUKANTA HALDER | 4.69 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone-II) | SM/07630 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Sachea Khali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VIII) | Assistant Engineer, Canning sub division |  | ORD/001555/2020-2021 | 1209/CSD | 15/12/2020 | 29/01/2021 | HALDER & CO. | 4.65 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone-II) | SM/07630 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Baria of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ IX) | Assistant Engineer, Canning sub division |  | ORD/001544/2020-2021 | 1203/CSD | 15/12/2020 | 29/01/2021 | SUSHANTA MANDAL | 4.73 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone-II) | SM/07630 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Sachea Khali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ V) | Assistant Engineer, Canning sub division |  | ORD/001453/2020-2021 | 1002/CSD | 13/11/2020 | 28/12/2020 | C.S. CONSTRUCTION | 4.79 | 9.58 | 199.82 | 100
9 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone-II) | SM/07630 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Baria of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VI) | Assistant Engineer, Canning sub division |  | ORD/001430/2020-2021 | 996/CSD | 13/11/2020 | 28/12/2020 | L.N. ENTERPRISE | 4.64 | 9.24 | 199.17 | 100
10 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone-II) | SM/07630 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Bugulakhali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VI) | Assistant Engineer, Canning sub division |  | ORD/001549/2020-2021 | 1204/CSD | 15/12/2020 | 29/01/2021 | SARKAR ENTERPRISE | 4.78 | 9.52 | 198.97 | 100
11 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone-II) | SM/07630 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Purba Bayar Sing of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ V) | Assistant Engineer, Canning sub division |  | ORD/001550/2020-2021 | 1205/CSD | 15/12/2020 | 29/01/2021 | SUKANTA HALDER | 4.78 | 9.53 | 199.24 | 100
12 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone-II) | SM/07630 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Baria of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - III) | Assistant Engineer, Canning sub division |  | ORD/001441/2020-2021 | 966/CSD | 07/11/2020 | 22/12/2020 | L.N. ENTERPRISE | 4.7 | 9.36 | 199.23 | 100
13 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone-II) | SM/07630 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Bugulakhali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ IV) | Assistant Engineer, Canning sub division |  | ORD/001445/2020-2021 | 998/CSD | 13/11/2020 | 28/12/2020 | M/S M.G.CONSTRUCTION | 4.72 | 9.42 | 199.47 | 100
14 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone-II) | SM/07630 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Bugulakhali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ V) | Assistant Engineer, Canning sub division |  | ORD/001446/2020-2021 | 999/CSD | 13/11/2020 | 28/12/2020 | SUSHANTA MANDAL | 4.79 | 9.56 | 199.53 | 100
15 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone-II) | SM/07630 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Sachea Khali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VI) | Assistant Engineer, Canning sub division |  | ORD/001552/2020-2021 | 1207/CSD | 15/12/2020 | 29/01/2021 | MODERN CONSTRUCTION | 4.73 | 9.42 | 199.15 | 100
16 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone-II) | SM/07630 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Baria of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ V) | Assistant Engineer, Canning sub division |  | ORD/001429/2020-2021 | 995/CSD | 13/11/2020 | 28/12/2020 | L.N. ENTERPRISE | 4.6 | 9.17 | 199.28 | 100
17 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone-II) | SM/07630 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Sachea Khali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ IV) | Assistant Engineer, Canning sub division |  | ORD/001452/2020-2021 | 1001/CSD | 13/11/2020 | 28/12/2020 | M/S M.G.CONSTRUCTION | 4.72 | 9.42 | 199.51 | 100
18 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone-II) | SM/07630 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Baria of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - II) | Assistant Engineer, Canning sub division |  | ORD/001440/2020-2021 | 965/CSD | 07/11/2020 | 22/12/2020 | M/S R.K.ENTERPRISE | 4.62 | 9.21 | 199.17 | 100
19 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone-II) | SM/07630 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Baria of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - IV) | Assistant Engineer, Canning sub division |  | ORD/001444/2020-2021 | 1007/CSD | 13/11/2020 | 28/12/2020 | L.N. ENTERPRISE | 4.67 | 9.31 | 199.39 | 100
20 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone-II) | SM/07630 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Bugulakhali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - II) | Assistant Engineer, Canning sub division |  | ORD/001447/2020-2021 | 1008/CSD | 13/11/2020 | 28/12/2020 | SUSHANTA MANDAL | 4.63 | 9.24 | 199.51 | 100
21 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone-II) | SM/07630 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Purba Bayar Sing of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ IV) | Assistant Engineer, Canning sub division |  | ORD/001448/2020-2021 | 1000/CSD | 13/11/2020 | 28/12/2020 | SUKANTA HALDER | 4.75 | 9.47 | 199.54 | 100
22 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone-II) | SM/07630 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Purba Bayar Sing of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - III) | Assistant Engineer, Canning sub division |  | ORD/001450/2020-2021 | 1010/CSD | 13/11/2020 | 28/12/2020 | SURYA ENTERPRISE | 4.74 | 8.81 | 185.86 | 100
23 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone-II) | SM/07630 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Purba Bayar Sing of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VI) | Assistant Engineer, Canning sub division |  | ORD/001551/2020-2021 | 1206/CSD | 15/12/2020 | 29/01/2021 | C.S. CONSTRUCTION | 4.75 | 9.47 | 199.62 | 100
24 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone-II) | SM/07630 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Sachea Khali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - III) | Assistant Engineer, Canning sub division |  | ORD/001458/2020-2021 | 1012/CSD | 13/11/2020 | 28/12/2020 | JAGANNATH ENTERPRISE | 4.77 | 4.74 | 99.39 | 100
25 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone-II) | SM/07630 | Retrofitting | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali Water Supply Scheme (Zone-I) including one year Operation & Maintenance of scheme, Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division |  | ORD/000848/2021-2022 | 3198/AD | 11/11/2021 | 11/11/2022 | UNITED BUILDERS | 99.47 | 7.65 | 7.69 | 63
26 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone-II) | SM/07630 | Retrofitting | Sinking of 250mm x 150mm dia. 350 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. -4 of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000475/2022-2023 | 5526/AD | 29/09/2022 | 29/10/2022 | SIMPLEX DRILLING CO. | 18.32 | 0 | 0 | 0
27 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone-II) | SM/07630 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Baria of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - I) | Assistant Engineer, Canning sub division |  | ORD/000631/2020-2021 | 845/CSD | 12/10/2020 | 26/11/2020 | PRASANTA MONDAL | 4.74 | 4.72 | 99.52 | 100
28 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone-II) | SM/07630 | Retrofitting | Relaying damaged pipeline for FHTC at Chunakhali W/S Scheme Chunakhali Primary School to H/O Shyamal Das and H/O Prasanta Das to Chowmatha at Buglakhali Mouza, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001633/2020-2021 | 1349/CSD | 06/01/2021 | 05/02/2021 | SUKANTA HALDER | 4.73 | 4.58 | 96.94 | 100
29 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone-II) | SM/07630 | Retrofitting | Relaying and repairing of damaged pipeline for FHTC at Chunakhali W/S Scheme at Khanka Sarif More to Sachiakhali FP School of Sachiakhali Mouza, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001619/2020-2021 | 1345/CSD | 04/01/2021 | 03/02/2021 | MODERN CONSTRUCTION | 4.82 | 4.78 | 99.24 | 100
30 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone-II) | SM/07630 | Retrofitting | Relaying damaged pipeline for FHTC at Chunakhali W/S Scheme at Laskarpara to PWD Road and H/O Ganesh Sardar to H/O Dinanath Sardar of Purba Bayar Sing Mouza and Sachiakhali Mouza, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001632/2020-2021 | 1348/CSD | 06/01/2021 | 05/02/2021 | MODERN CONSTRUCTION | 4.68 | 4.66 | 99.66 | 100
31 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone-II) | SM/07630 | Retrofitting | Repairing damaged pipeline for FHTC at Chunakhali W/S Scheme at Buglakhali Mouza, Purba Bayar Sing Mouza, Sachiakhali Mouza and Baria Mouza, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001637/2020-2021 | 1350/CSD | 06/01/2021 | 05/02/2021 | SUKANTA HALDER | 4.74 | 4.65 | 97.99 | 100
32 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone-II) | SM/07630 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Bugulakhali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - I) | Assistant Engineer, Canning sub division |  | ORD/000607/2020-2021 | 846/CSD | 12/10/2020 | 26/11/2020 | SUSHANTA MANDAL | 4.73 | 9.46 | 199.74 | 0
33 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone-II) | SM/07630 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Purba Bayar Sing of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - II) | Assistant Engineer, Canning sub division |  | ORD/000608/2020-2021 | 848/CSD | 12/10/2020 | 26/11/2020 | SUKANTA HALDER | 4.74 | 9.45 | 199.54 | 0
34 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone-II) | SM/07630 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Purba Bayar Sing of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - I) | Assistant Engineer, Canning sub division |  | ORD/000650/2020-2021 | 847/CSD | 12/10/2020 | 26/11/2020 | KAMALA ENTERPRISE (I) | 4.72 | 9.42 | 199.49 | 0
Total | [13 empty] | 268.88 | 213.86 | 79.54