## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Nagartala Water Suppl | SM/07633 | Retrofitting | Construction of day to day annual Operation, repair & Maintenance of CI/DI/AC/UPVC Riising main & distribution system for different zones at Nagartala (zone-II) W/S Scheme under Canning Sub-Division of Alipore Division, PHE Dte.. | Assistant Engineer, Canning sub division |  | ORD/003183/2020-2021 | 501/CSD | 05/08/2020 | 05/08/2020 | MODERN CONSTRUCTION | 1.29 | 1.29 | 100 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Nagartala Water Suppl | SM/07633 | Retrofitting | Day to day annual operation, repair & maintenance of CI/DI/AC/UPVC Rising Main & Distribution System for different zones at Nagartala W/S Scheme (Zone-II) under Canning Sub Division of Alipore Division, PHE Dte. [From 01.01.2021 to 23.03.2021] | Assistant Engineer, Canning sub division |  | ORD/002421/2020-2021 | 1291/CSD | 30/12/2020 | 22/03/2021 | MODERN CONSTRUCTION | 1.84 | 0.96 | 52.09 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Nagartala Water Suppl | SM/07633 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Nagartala Water Supply Scheme, Block - Canning-II, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000066/2021-2022 | 708/AD | 10/06/2021 | 10/06/2022 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 223.57 | 151.08 | 67.57 | 70
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Nagartala Water Suppl | SM/07633 | Retrofitting | Day to day annual operation, repair & maintenance of CI/DI/AC/UPVC Rising Main & Distribution System for different zones at Nagartala (Zone-II) W/S Scheme under Canning Sub Division of Alipore Division, PHE Dte. [365 Days] | Assistant Engineer, Canning sub division |  | ORD/002229/2020-2021 | 2030/CSD | 24/03/2021 | 24/03/2022 | MODERN CONSTRUCTION | 2.77 | 1.21 | 43.67 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Nagartala Water Suppl | SM/07633 | Retrofitting | Laying distribution system of Nagartala Water Supply Scheme (Zone-II) Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000587/2022-2023 | 5863/AD | 18/10/2022 | 17/11/2022 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 45.64 | 44.97 | 98.54 | 0
Total | [13 empty] | 275.11 | 199.51 | 72.52