## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 14 (fourteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Banibadabelekhali Wat | SM/07634 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Banibadabelekhali Water Supply Scheme, Block - Canning-I, South 24 Parganas District under Canning Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year | Assistant Engineer, Canning sub division |  | ORD/000087/2020-2021 | 5123/AD | 08/02/2021 | 08/02/2022 | DIVINE | 162.5 | 253.67 | 156.11 | 92
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 14 (fourteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Banibadabelekhali Wat | SM/07634 | Retrofitting | Construction of concrete road (balanced portion) in OHR premises of Pump House no. - 1 of Banibadabelekhali W/S Scheme, Block - Canning I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000370/2025-2026 | 671/CSD | 26/05/2025 | 25/06/2025 | A.N.S. ENTERPRISE | 1.71 | 0 | 0 | 0
Total | [13 empty] | 164.2 | 253.67 | 154.49