## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Taktipur Abad W/S Scheme incl | SM/07635 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Paschim Para and Taktipur (Part) for Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Phase-I) | Assistant Engineer, Kakdwip Sub Division |  | ORD/001889/2020-2021 | 1311/KSD | 23/02/2021 | 05/03/2021 | M/S THREE STAR & CON. | 4.38 | 4.01 | 91.49 | 92
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Taktipur Abad W/S Scheme incl | SM/07635 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Naskarchak for Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Phase-I) | Assistant Engineer, Kakdwip Sub Division |  | ORD/001919/2020-2021 | 1329/KSD | 23/02/2021 | 05/03/2021 | MOUMITA ENTERPRISE | 4.39 | 4.04 | 91.94 | 93
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Taktipur Abad W/S Scheme incl | SM/07635 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dakshin Para and Taktipur (Part) for Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Phase-II) | Assistant Engineer, Kakdwip Sub Division |  | ORD/001925/2020-2021 | 1337/KSD | 23/02/2021 | 05/03/2021 | SUFIA ENTERPRISE | 4.39 | 4.04 | 92.06 | 93
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Taktipur Abad W/S Scheme incl | SM/07635 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Purba Para and Taktipur (Part) for Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Phase-II) | Assistant Engineer, Kakdwip Sub Division |  | ORD/001927/2020-2021 | 1339/KSD | 23/02/2021 | 05/03/2021 | M/S. MA LAXMI ENTERPRISE | 4.39 | 4.05 | 92.34 | 93
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Taktipur Abad W/S Scheme incl | SM/07635 | Retrofitting | Laying UPVC Pipe Line for Providing House Connection to the Households of Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001929/2020-2021 | 1342/KSD | 23/02/2021 | 10/03/2021 | SARADA CONSTRUCTION | 3.07 | 3.04 | 99.14 | 100
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Taktipur Abad W/S Scheme incl | SM/07635 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Paschim Para and Taktipur (Part) for Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Phase-II) | Assistant Engineer, Kakdwip Sub Division |  | ORD/001931/2020-2021 | 1344/KSD | 23/02/2021 | 05/03/2021 | SUFIA ENTERPRISE | 4.38 | 3.74 | 85.39 | 86
7 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Taktipur Abad W/S Scheme incl | SM/07635 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Madhya Para and Taktipur (Part) for Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Phase-II) | Assistant Engineer, Kakdwip Sub Division |  | ORD/001933/2020-2021 | 1346/KSD | 23/02/2021 | 05/03/2021 | M/S. MAA MENAKA ENTERPRISE | 4.39 | 3.98 | 90.69 | 91
8 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Taktipur Abad W/S Scheme incl | SM/07635 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Narayanpur and Taktipur (Part) for Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Phase-II) | Assistant Engineer, Kakdwip Sub Division |  | ORD/001972/2020-2021 | 1341/KSD | 23/02/2021 | 05/03/2021 | M/S MAA BASANTI ENTERPRISE | 4.38 | 4.02 | 91.75 | 92
9 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Taktipur Abad W/S Scheme incl | SM/07635 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dakshin Para and Taktipur (Part) for Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Phase-I) | Assistant Engineer, Kakdwip Sub Division |  | ORD/001870/2020-2021 | 1301/KSD | 23/02/2021 | 05/03/2021 | M/S THREE STAR & CON. | 4.39 | 4.07 | 92.66 | 93
10 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Taktipur Abad W/S Scheme incl | SM/07635 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Madhya Para and Taktipur (Part) for Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Phase-I) | Assistant Engineer, Kakdwip Sub Division |  | ORD/001874/2020-2021 | 1303/KSD | 23/02/2021 | 05/03/2021 | M/S. MAA MENAKA ENTERPRISE | 4.38 | 4.04 | 92.12 | 93
11 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Taktipur Abad W/S Scheme incl | SM/07635 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Purba Para and Taktipur (Part) for Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Phase-I) | Assistant Engineer, Kakdwip Sub Division |  | ORD/001907/2020-2021 | 1322/KSD | 23/02/2021 | 05/03/2021 | M/S. MA LAXMI ENTERPRISE | 4.38 | 4.04 | 92.11 | 93
12 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Taktipur Abad W/S Scheme incl | SM/07635 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Narayanpur and Taktipur (Part) for Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Phase-I) | Assistant Engineer, Kakdwip Sub Division |  | ORD/001970/2020-2021 | 1335/KSD | 23/02/2021 | 05/03/2021 | M/S MAA BASANTI ENTERPRISE | 4.38 | 4.04 | 92.23 | 93
13 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Taktipur Abad W/S Scheme incl | SM/07635 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Janarchak for Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Phase-I) | Assistant Engineer, Kakdwip Sub Division |  | ORD/001921/2020-2021 | 1331/KSD | 23/02/2021 | 05/03/2021 | MOUMITA ENTERPRISE | 4.39 | 4.04 | 92.06 | 93
14 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Taktipur Abad W/S Scheme incl | SM/07635 | Retrofitting | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Executive Engineer, Alipore Division, PHE Dte. for the period from 29.09.2022 to 30.11.2022 | Assistant Engineer, Kakdwip Sub Division |  | ORD/000776/2022-2023 | 266/HQ-II/AD | 28/09/2022 | 30/11/2022 | PRIYANKI SADHUKHAN | 0.8 | 0.68 | 85.57 | 85
15 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Taktipur Abad W/S Scheme incl | SM/07635 | Retrofitting | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 1st and 2nd Tubewell Site for Augmentation of Taktipur (Zone-I & II) W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/11876) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000412/2024-2025 | 3063/AD | 25/07/2024 | 08/09/2024 | RAJ ENTERPRISE | 38.71 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Taktipur Abad W/S Scheme incl | SM/07635 | Retrofitting | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connection etc. for Augmentation of Taktipur Zone- II W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) (SM/11876) (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000466/2024-2025 | 3461/AD | 23/08/2024 | 07/10/2024 | GHOSH CONSTRUCTION | 18.54 | 0 | 0 | 0
17 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Taktipur Abad W/S Scheme incl | SM/07635 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000824/2023-2024 | 669/AD | 30/01/2024 | 30/01/2024 | Resource Division | 8.82 | 0 | 0 | 0
18 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Taktipur Abad W/S Scheme incl | SM/07635 | Retrofitting | Hire Charges Vehicle bill (June '22 to Oct'22) |  |  | BILL/03273/2023-2024 |  | 20/03/2024 | 20/03/2024 | RAJKUMAR MANNA | 6.29 | 0 | 0 | 0
19 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Taktipur Abad W/S Scheme incl | SM/07635 | Retrofitting | Vehicle bill for month of June'22 to August'22 |  |  | BILL/03275/2023-2024 | BP-2023-24-1259 | 26/03/2024 | 26/03/2024 | RAJKUMAR MANNA | 1.1 | 0 | 0 | 0
Total | [13 empty] | 129.96 | 51.84 | 39.89