## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 65 (sixty five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Suryanagar W/S Scheme i | SM/07636 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households at Suryanagar Water Supply scheme, Block - Kakdwip, South 24 Parganas District under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001567/2021-2022 | 6829/AD | 23/03/2022 | 07/05/2022 | M/S B. ENTERPRISE | 113.06 | 105.3 | 93.14 | 94
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 65 (sixty five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Suryanagar W/S Scheme i | SM/07636 | Retrofitting | Preparation of DPR including estimate for Providing FHTC at Ramchandranagar W/S Scheme (Phase-A), Srinagar W/S Scheme (Phase-A), Suryanagar W/S Scheme (Phase-A) & Taktipur W/S Scheme (Phase-A) W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. [W/O No. 515/KSD, 24.08.21, T.No. 1801/AD, 21-22] |  |  | VCH/002605/2021-2022 | BP-2021-22-508 | 22/03/2022 | 22/03/2022 | LEMNISCATE | 4.7 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 65 (sixty five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Suryanagar W/S Scheme i | SM/07636 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000842/2023-2024 | 690/AD | 30/01/2024 | 30/01/2024 | Resource Division | 24.01 | 0 | 0 | 0
Total | [13 empty] | 141.77 | 105.3 | 74.27