## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 20 (twenty) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dharmatala Water Supply | SM/07640 | Retrofitting | Laying pipe line Badhukulla and Naliakhali of Dharmatala Water Supply Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000588/2022-2023 | 5864/AD | 18/10/2022 | 02/11/2022 | SAB ENGINEERING WORKS | 9.27 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 20 (twenty) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dharmatala Water Supply | SM/07640 | Retrofitting | Sinking of 03 (three) Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Dharmatala W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001348/2022-2023 | 10215/AD | 19/01/2023 | 20/03/2023 | B.K. ENTERPRISE. | 59.91 | 0 | 0 | 90
3 | SOUTH 24 PARGANAS |  | Central Drilling | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 20 (twenty) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dharmatala Water Supply | SM/07640 | Retrofitting | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MMX150MMX 300 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR DHARMATALA W/S SCH (REPLACEMENT TW-IV), CANNING-I BLOCK UNDER SOUTH 24 PGS DISTRICT, CDD, PHE DTE. |  |  | ORD/000315/2022-2023 | 54/CDD | 08/04/2022 | 08/05/2022 | C.M. ENTERPRISE | 14.55 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 20 (twenty) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dharmatala Water Supply | SM/07640 | Retrofitting | Laying pipe line at Badhukulla of Dharmatala W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000300/2023-2024 | 187/CSD | 23/05/2023 | 22/06/2023 | GOUTAM HALDAR (I) | 0.95 | 0 | 0 | 100
5 | SOUTH 24 PARGANAS |  | Central Drilling | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 20 (twenty) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dharmatala Water Supply | SM/07640 | Retrofitting | ADDITIONAL TRANSPORTATION OF WASHED GRAVELS, SEALING OF SALINE ZONE AND OTHERS FOR CONSTRUCTION OF TUBEWELL IN DHAMATALA W/S SCHEME(REPLACEMENT TW-IV), CANNING -I BLOCK UNDER CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000507/2022-2023 | 42/CMSD-II | 16/02/2023 | 26/02/2023 | C.M. ENTERPRISE | 0.82 | 0 | 0 | 100
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 20 (twenty) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dharmatala Water Supply | SM/07640 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Dharmatala Water Supply Scheme, Block - Canning-I, South 24 Parganas District under Canning Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000082/2020-2021 | 5305/AD | 18/02/2021 | 18/02/2022 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 257.73 | 47.48 | 18.42 | 78
7 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 20 (twenty) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dharmatala Water Supply | SM/07640 | Retrofitting | Laying pipe line to connect the uncovered habitations at Mouza-Amtala Bhadri, Dakshin Kalikatala, Herobhanga and Basur Chak of Dharmatala Water Supply Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/001063/2021-2022 | 5298/AD | 04/01/2022 | 05/03/2022 | SAHANA ENTERPRISE | 28.74 | 0 | 0 | 100
8 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 20 (twenty) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dharmatala Water Supply | SM/07640 | Retrofitting | Laying rising main from tubewell no. 4 at Dharmatala W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001407/2023-2024 | 1146/CSD | 01/11/2023 | 01/12/2023 | GOUTAM HALDAR (I) | 1.92 | 0 | 0 | 100
Total | [13 empty] | 373.89 | 47.48 | 12.7