## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - VI) | Assistant Engineer, Canning sub division |  | ORD/001466/2020-2021 | 1018/CSD | 23/11/2020 | 07/01/2021 | SUKANTA HALDER | 4.71 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - IX) | Assistant Engineer, Canning sub division |  | ORD/001472/2020-2021 | 1021/CSD | 23/11/2020 | 07/01/2021 | M/S TAMAL CHAKRABORTY | 4.72 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - X) | Assistant Engineer, Canning sub division |  | ORD/001473/2020-2021 | 1022/CSD | 23/11/2020 | 07/01/2021 | M/S. PROMILA CONSTRUCTION | 4.62 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Gola Bari of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - VI) | Assistant Engineer, Canning sub division |  | ORD/001474/2020-2021 | 1023/CSD | 23/11/2020 | 07/01/2021 | R.G. ENTERPRISE (I) | 4.78 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Gola Bari of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - VII) | Assistant Engineer, Canning sub division |  | ORD/001475/2020-2021 | 1029/CSD | 24/11/2020 | 08/01/2021 | BANERJEE ENTERPRISE | 4.73 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Modhu Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - VI) | Assistant Engineer, Canning sub division |  | ORD/001477/2020-2021 | 1031/CSD | 24/11/2020 | 08/01/2021 | GANGA TUBEWELL AND HARDWARE | 4.79 | 4.66 | 97.3 | 100
7 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ XV) | Assistant Engineer, Canning sub division |  | ORD/001557/2020-2021 | 1212/CSD | 15/12/2020 | 29/01/2021 | M/S. MANABESH ROY | 4.65 | 4.64 | 99.76 | 100
8 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ XI) | Assistant Engineer, Canning sub division |  | ORD/001455/2020-2021 | 1003/CSD | 13/11/2020 | 28/12/2020 | MONCON INDIA | 4.7 | 9.39 | 199.67 | 100
9 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - VII) | Assistant Engineer, Canning sub division |  | ORD/001470/2020-2021 | 1019/CSD | 23/11/2020 | 07/01/2021 | A.S.A.CONSTRUCTION AND CONSULTANT | 4.77 | 4.76 | 99.92 | 100
10 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Gola Bari of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ IX) | Assistant Engineer, Canning sub division |  | ORD/001456/2020-2021 | 1005/CSD | 13/11/2020 | 28/12/2020 | MODERN CONSTRUCTION | 4.74 | 0 | 0 | 100
11 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Modhu Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ X) | Assistant Engineer, Canning sub division |  | ORD/001457/2020-2021 | 1006/CSD | 13/11/2020 | 28/12/2020 | SOURAV NASKAR | 4.79 | 4.78 | 99.87 | 100
12 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Gola Bari of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - VIII) | Assistant Engineer, Canning sub division |  | ORD/001476/2020-2021 | 1030/CSD | 24/11/2020 | 08/01/2021 | MODERN CONSTRUCTION | 4.7 | 0 | 0 | 100
13 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Modhu Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - IX) | Assistant Engineer, Canning sub division |  | ORD/001480/2020-2021 | 1034/CSD | 24/11/2020 | 08/01/2021 | S.C. ENTERPRISE (I) | 4.66 | 4.58 | 98.37 | 100
14 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Modhu Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - VII) | Assistant Engineer, Canning sub division |  | ORD/001478/2020-2021 | 1032/CSD | 24/11/2020 | 08/01/2021 | ASHIS ENTERPRISE | 4.72 | 4.21 | 89.13 | 100
15 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Modhu Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - VIII) | Assistant Engineer, Canning sub division |  | ORD/001479/2020-2021 | 1033/CSD | 24/11/2020 | 08/01/2021 | GANGA TUBEWELL AND HARDWARE | 4.69 | 4.67 | 99.73 | 100
16 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ XVI) | Assistant Engineer, Canning sub division |  | ORD/001558/2020-2021 | 1214/CSD | 15/12/2020 | 29/01/2021 | D.R.CONSTRUCTION | 4.6 | 4.54 | 98.54 | 100
17 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ XIV) | Assistant Engineer, Canning sub division |  | ORD/001556/2020-2021 | 1211/CSD | 15/12/2020 | 29/01/2021 | M/S M3 SOLUTION | 4.7 | 9.39 | 199.61 | 100
18 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - XIX) | Assistant Engineer, Canning sub division |  | ORD/001751/2020-2021 | 1452/CSD | 27/01/2021 | 13/03/2021 | KIRON CONSTRUCTION | 4.57 | 3.88 | 85.05 | 100
19 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - XVII) | Assistant Engineer, Canning sub division |  | ORD/001747/2020-2021 | 1450/CSD | 27/01/2021 | 13/03/2021 | KIRON CONSTRUCTION | 4.61 | 4.17 | 90.48 | 100
20 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - XVIII) | Assistant Engineer, Canning sub division |  | ORD/001748/2020-2021 | 1451/CSD | 27/01/2021 | 13/03/2021 | KIRON CONSTRUCTION | 4.69 | 4.34 | 92.53 | 100
21 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ XIII) | Assistant Engineer, Canning sub division |  | ORD/002039/2020-2021 | 1210/CSD | 15/12/2020 | 29/01/2021 | M/S ARIYAN ENTERPRISE | 4.72 | 4.71 | 99.73 | 100
22 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - XX) | Assistant Engineer, Canning sub division |  | ORD/001754/2020-2021 | 1453/CSD | 27/01/2021 | 13/03/2021 | KIRON CONSTRUCTION | 4.65 | 4.5 | 96.84 | 100
23 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ XII) | Assistant Engineer, Canning sub division |  | ORD/001506/2020-2021 | 1004/CSD | 13/11/2020 | 28/12/2020 | M/S KRISHNA MONDAL | 4.75 | 9.49 | 199.78 | 100
24 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - VIII) | Assistant Engineer, Canning sub division |  | ORD/001471/2020-2021 | 1020/CSD | 23/11/2020 | 07/01/2021 | RAKTIM ENTERPRISE | 4.69 | 4.68 | 99.71 | 100
25 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (1500 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000337/2023-2024 | 1939/AD | 02/08/2023 | 31/10/2023 | KIRON CONSTRUCTION | 126.68 | 0 | 0 | 0
26 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Kripa Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - I) | Assistant Engineer, Canning sub division |  | ORD/000630/2020-2021 | 869/CSD | 12/10/2020 | 26/11/2020 | SAHANA ENTERPRISE | 4.74 | 4.74 | 99.84 | 100
27 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Modhu Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - IV) | Assistant Engineer, Canning sub division |  | ORD/000624/2020-2021 | 867/CSD | 12/10/2020 | 26/11/2020 | ASHIS ENTERPRISE | 4.72 | 4.71 | 99.8 | 100
28 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Modhu Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - V) | Assistant Engineer, Canning sub division |  | ORD/000625/2020-2021 | 868/CSD | 12/10/2020 | 26/11/2020 | DEY ENTERPRISE (III) | 4.74 | 4.74 | 99.89 | 100
29 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Modhu Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - I) | Assistant Engineer, Canning sub division |  | ORD/000621/2020-2021 | 864/CSD | 12/10/2020 | 26/11/2020 | GANGA TUBEWELL AND HARDWARE | 4.74 | 4.72 | 99.73 | 100
30 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Modhu Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - II) | Assistant Engineer, Canning sub division |  | ORD/000622/2020-2021 | 865/CSD | 12/10/2020 | 26/11/2020 | M/S. M.K. NASKAR & CONSTRUCTION | 4.73 | 4.72 | 99.76 | 100
31 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Gola Bari of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - IV) | Assistant Engineer, Canning sub division |  | ORD/000619/2020-2021 | 862/CSD | 12/10/2020 | 26/11/2020 | ARFIN CONSTRUCTION | 4.75 | 4.68 | 98.63 | 100
32 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Laying pipe line for FHTC work at Budhkhali W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000996/2021-2022 | 991/CSD | 26/10/2021 | 25/11/2021 | MODERN CONSTRUCTION | 3.74 | 3.72 | 99.49 | 100
33 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Extension of pipeline for FHTC work of Budhkhali Piped Water Supply Scheme Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001468/2021-2022 | 1490/CSD | 09/02/2022 | 01/03/2022 | MITRA ASSOCIATE | 4.6 | 4.59 | 99.78 | 100
34 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Repairing & relaying of damaged pipeline for FHTC work of Budhkhali Piped Water Supply Scheme Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001469/2021-2022 | 1491/CSD | 09/02/2022 | 01/03/2022 | ASHIS ENTERPRISE | 4.56 | 4.56 | 99.95 | 100
35 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Gola Bari of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - II) | Assistant Engineer, Canning sub division |  | ORD/000617/2020-2021 | 860/CSD | 12/10/2020 | 26/11/2020 | C.S. CONSTRUCTION | 4.73 | 4.63 | 97.88 | 95
36 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Gola Bari of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - III) | Assistant Engineer, Canning sub division |  | ORD/000618/2020-2021 | 861/CSD | 12/10/2020 | 26/11/2020 | SARKAR CONSTRUCTION | 4.75 | 9.44 | 198.92 | 0
37 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Gola Bari of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - V) | Assistant Engineer, Canning sub division |  | ORD/000620/2020-2021 | 863/CSD | 12/10/2020 | 26/11/2020 | KUNDU CONSTRUCTION CO. | 4.74 | 9.43 | 198.87 | 0
38 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Modhu Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - III) | Assistant Engineer, Canning sub division |  | ORD/000623/2020-2021 | 866/CSD | 12/10/2020 | 26/11/2020 | M/S. MANABESH ROY | 4.74 | 9.48 | 199.9 | 0
39 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - IV) | Assistant Engineer, Canning sub division |  | ORD/000614/2020-2021 | 853/CSD | 12/10/2020 | 26/11/2020 | SUKANTA HALDER | 4.74 | 4.72 | 99.72 | 0
40 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Laying of pipeline for providing house connection from H/O Rajkumar Sardar to H/O Bhagyadhar Sardar of Pakhirali habitation under Budhkhali W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/002028/2020-2021 | 1517/CSD | 10/02/2021 | 12/03/2021 | MONCON INDIA | 0.43 | 0.85 | 198.67 | 0
41 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - I) | Assistant Engineer, Canning sub division |  | ORD/000611/2020-2021 | 850/CSD | 12/10/2020 | 26/11/2020 | DIPA CHHETRI | 4.74 | 9.47 | 199.76 | 0
42 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | SM/07641 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Gola Bari of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - I) | Assistant Engineer, Canning sub division |  | ORD/000616/2020-2021 | 855/CSD | 12/10/2020 | 26/11/2020 | MODERN CONSTRUCTION | 4.74 | 4.73 | 99.87 | 0
Total | [13 empty] | 314.34 | 185.32 | 58.96