## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bharatgarh Water Supply | SM/07642 | Retrofitting | Laying High Density Poly-ethylene Pipe in connection with functional house hold tap connection (FHTC) in Bharatgarh W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) | Assistant Engineer, Canning sub division |  | ORD/001735/2020-2021 | 1438/CSD | 25/01/2021 | 24/02/2021 | SRIJON ENTERPRISE | 4.8 | 4.79 | 99.89 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bharatgarh Water Supply | SM/07642 | Retrofitting | Laying High Density Poly-ethylene Pipe in connection with functional house hold tap connection (FHTC) in Bharatgarh W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Part-II) | Assistant Engineer, Canning sub division |  | ORD/001736/2020-2021 | 1439/CSD | 25/01/2021 | 24/02/2021 | SRIJON ENTERPRISE | 4.69 | 4.34 | 92.63 | 98
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bharatgarh Water Supply | SM/07642 | Retrofitting | Providing support service for detail surveying, cross checking of available LOP with making permission drawing for other department by using Survey Instruments at Kolkata-Basanti Road (SH 3A, from chainage 71.000 to 86.790), Basanti-Godkhali Road (SH 3A, from chainage 0.000 to 9.894) and Bharatgar Bazar to Ganga Mela Road (from chainage 5.800 to 11.900) like Remotely Piloted Aircraft System / DGPS / Total Station etc. | Assistant Engineer, Canning sub division |  | ORD/000272/2022-2023 | 265/CSD | 19/05/2022 | 18/06/2022 | FIDERE MARINE SERVICES PVT. LTD. | 1.82 | 1.74 | 95.77 | 98
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bharatgarh Water Supply | SM/07642 | Retrofitting | Construction of boundary wall at Pump House No. - 2 at Ground Water Based Augmentation Piped Water Supply Scheme of Bharatgarh W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000750/2024-2025 | 4422/AD | 05/11/2024 | 05/12/2024 | RAKTIM ENTERPRISE | 12.56 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bharatgarh Water Supply | SM/07642 | Retrofitting | Construction of boundary wall at Pump House No. - 1 at Ground Water Based Augmentation Piped Water Supply Scheme of Bharatgarh W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000749/2024-2025 | 4421/AD | 05/11/2024 | 05/12/2024 | RAKTIM ENTERPRISE | 27.39 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bharatgarh Water Supply | SM/07642 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000400/2023-2024 | 358/AD | 19/01/2024 | 19/01/2024 | Resource Division | 3.39 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bharatgarh Water Supply | SM/07642 | Retrofitting | Inter connection & rising main with supply of specials at TW No. 1 & 5 of Bharatgarh W/S Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/003338/2024-2025 | 36./CSD | 09/01/2025 | 08/02/2025 | RAKTIM ENTERPRISE | 2.04 | 0 | 0 | 0
Total | [13 empty] | 56.67 | 10.88 | 19.19