## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Goran Bose Water Supply Sc | SM/07644 | Retrofitting | Construction of boundary wall at Pump House No. - 2 at Ground Water Based Augmentation Piped Water Supply Scheme of Goranbose W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000748/2024-2025 | 4420/AD | 05/11/2024 | 05/12/2024 | MODERN CONSTRUCTION | 20.83 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Goran Bose Water Supply Sc | SM/07644 | Retrofitting | Construction of boundary wall at Pump House No. - 1 at Ground Water Based Augmentation Piped Water Supply Scheme of Goranbose W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000747/2024-2025 | 4419/AD | 05/11/2024 | 05/12/2024 | S.S. CONSTRUCTION | 29.61 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Goran Bose Water Supply Sc | SM/07644 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000399/2023-2024 | 357/AD | 19/01/2024 | 19/01/2024 | Resource Division | 3.82 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Goran Bose Water Supply Sc | SM/07644 | Retrofitting | Construction of 600 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height including foundation, pipeline connection and cost of pipes , specials etc. of Goranbose piped water supply scheme of Basanti Block under Canning Sub- Division of Alipore Division, PHE Dte. (SM/05716) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/002095/2024-2025 | 351/AD | 28/01/2025 | 24/11/2025 | MS SINHA ROY & CO | 181.43 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Goran Bose Water Supply Sc | SM/07644 | Retrofitting | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Goranbose W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001711/2022-2023 | 11675/AD | 20/02/2023 | 09/02/2025 | A 8 T CONSTRUCTION | 7.09 | 0 | 0 | 100
Total | [13 empty] | 242.79 | 0 | 0