## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Shibganj W/S Scheme in | SM/07749 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Gangadharpur for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001785/2020-2021 | 1230/KSD | 23/02/2021 | 05/03/2021 | SRI DURGA ENTERPRISE | 4.39 | 0 | 0 | 95
2 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Shibganj W/S Scheme in | SM/07749 | Retrofitting | Laying UPVC pipe line for maintaining Functional Household Tap Connection at Pathar Pratima Bazar Area for Dakshin Shibganj piped water supply Scheme, Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001789/2020-2021 | 1234/KSD | 23/02/2021 | 05/03/2021 | M/S B. ENTERPRISE | 4.42 | 4.4 | 99.62 | 100
3 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Shibganj W/S Scheme in | SM/07749 | Retrofitting | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Dakshin Shibganj & Laxmijanardanpur W/S Scheme & it's adjacent areas, Block - Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001049/2021-2022 | 2332/AD | 09/09/2021 | 16/09/2021 | INDRANIL DUTTA & ASSOCIATES | 4.28 | 4.28 | 100 | 100
4 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Shibganj W/S Scheme in | SM/07749 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Dakshin Sibnagar Water Supply Scheme, Block - Kakdwip, South 24 Pgs. District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001207/2020-2021 | 2103/AD | 01/10/2020 | 01/10/2021 | M/S B. ENTERPRISE | 64.82 | 12.15 | 18.74 | 95
5 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Shibganj W/S Scheme in | SM/07749 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000773/2023-2024 | 607/AD | 29/01/2024 |  | Resource Division | 7.26 | 0 | 0 | 0
6 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Shibganj W/S Scheme in | SM/07749 | Retrofitting | Providing Valves for maintaining proper pressure head at dam area in Dakshin Shibganj W/S Scheme, Block - Pathar Pratima in connection with Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) under Jal Swapna under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000395/2020-2021 | 957/KSD | 03/11/2020 | 03/12/2020 | M/S B. ENTERPRISE | 4.18 | 4.17 | 99.8 | 0
7 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Shibganj W/S Scheme in | SM/07749 | Retrofitting | Laying PUVC pipe line for providing Functional Household Tap Connection for Dakshin Shibganj piped water supply Scheme From Node Point - (30-31, 16-17, 3-3A, 27-28), Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000504/2020-2021 | 1076/KSD | 19/12/2020 | 13/01/2021 | M/S B. ENTERPRISE | 4.79 | 4.78 | 99.85 | 0
8 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Shibganj W/S Scheme in | SM/07749 | Retrofitting | Laying PUVC pipe line for providing Functional Household Tap Connection for Dakshin Shibganj piped water supply Scheme From Node Point - (22-23, 21-25, 19-30, 8-9), Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000480/2020-2021 | 1058/KSD | 19/12/2020 | 13/01/2021 | M/S B. ENTERPRISE | 4.78 | 4.77 | 99.91 | 0
9 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Shibganj W/S Scheme in | SM/07749 | Retrofitting | Laying PUVC pipe line for providing Functional Household Tap Connection for Dakshin Shibganj piped water supply Scheme From Node Point - (16-17, 11-12, 5-6, 2-3), Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000485/2020-2021 | 1062/KSD | 19/12/2020 | 13/01/2021 | M/S B. ENTERPRISE | 4.75 | 4.74 | 99.92 | 0
10 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Shibganj W/S Scheme in | SM/07749 | Retrofitting | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Dakshin Shibganj W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/10482) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000418/2024-2025 | 3069/AD | 25/07/2024 | 08/09/2024 | M/S B. ENTERPRISE | 28.74 | 0 | 0 | 0
Total | [13 empty] | 132.4 | 39.3 | 29.68