## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XI, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/07750 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households of Mouza-Kailashpur (Part-B) in Nandakumarpur Zone II piped water supply scheme, District South 24 Parganas, Block - Mathurapur-II under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001185/2021-2022 | 541/RSD | 30/11/2021 | 29/01/2022 | M/S. L.P. CONSTRUCTION | 4.79 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XI, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/07750 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households of Mouza-Kailashpur (Part-A) in Nandakumarpur Zone II piped water supply scheme, District South 24 Parganas, Block - Mathurapur-II under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001205/2021-2022 | 523/RSD | 18/11/2021 | 17/01/2022 | M/S. L.P. CONSTRUCTION | 4.79 | 0 | 0 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XI, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/07750 | Retrofitting | Functional Household Tap Connection (FHTC) to the households at Purba Boler Gheri, Mouza-Mahabatnagar in Nandakumarpur Zone-II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E.Dte. (Part-II) | Assistant Engineer, Raidighi sub division |  | ORD/000579/2020-2021 | 505/RSD | 24/12/2020 | 22/02/2021 | A.P.C.ENGINEERS CO-OPERATIVE SOCIETY LTD. | 2.39 | 0 | 0 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XI, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/07750 | Retrofitting | Providing 110 nos Functional Household Tap Connection (FHTC) to the households at Janar Gheri, Mouza-Mahabatnagar in Nandakumarpur Zone-II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/000311/2020-2021 | 328/A/RSD | 30/09/2020 | 15/10/2020 | TIYASHA ENTERPRISE | 4.73 | 0 | 0 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XI, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/07750 | Retrofitting | Providing 110 nos Functional Household Tap Connection (FHTC) to the households at Marayari Gheri, Mouza-Mahabatnagar in Nandakumarpur Zone-II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Raidighi sub division |  | ORD/000324/2020-2021 | 382/RSD | 16/10/2020 | 15/11/2020 | TIYASHA ENTERPRISE | 4.73 | 0 | 0 | 100
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XI, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/07750 | Retrofitting | Providing 110 nos Functional Household Tap Connection (FHTC) to the households at Purba Boler Gheri, Mouza-Mahabatnagar in Nandakumarpur Zone-II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Raidighi sub division |  | ORD/000326/2020-2021 | 383/RSD | 16/10/2020 | 15/11/2020 | TIYASHA ENTERPRISE | 4.74 | 0 | 0 | 100
7 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XI, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/07750 | Retrofitting | Providing 110 nos Functional Household Tap Connection (FHTC) to the households at Purba Goler Gheri, Mouza-Jagannath Chak in Nandakumarpur Zone-II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/000312/2020-2021 | 329/A/RSD | 30/09/2020 | 15/10/2020 | M/S. JHARNA ENTERPRISE | 4.73 | 4.62 | 97.64 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XI, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/07750 | Retrofitting | Functional Household Tap Connection (FHTC) to the households at Manager Gheri, Mouza-Kailashpur in Nandakumarpur Zone-II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division |  | ORD/000361/2020-2021 | 428/RSD | 23/11/2020 | 22/01/2021 | M/S. JHARNA ENTERPRISE | 4.82 | 4.8 | 99.52 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XI, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/07750 | Retrofitting | Functional Household Tap Connection (FHTC) to the households at Janar Gheri, Mouza-Mahabatnagar in Nandakumarpur Zone-II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E.Dte. (Part-II) | Assistant Engineer, Raidighi sub division |  | ORD/000359/2020-2021 | 426/RSD | 23/11/2020 | 22/01/2021 | TIYASHA ENTERPRISE | 4.82 | 0 | 0 | 100
10 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XI, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/07750 | Retrofitting | Functional Household Tap Connection (FHTC) to the households at Janar Gheri & Sarda Gheri, Mouza-Kailashpur in Nandakumarpur Zone-II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division |  | ORD/000362/2020-2021 | 429/RSD | 23/11/2020 | 22/01/2021 | M/S. R.M. CONSTRUCTION | 4.82 | 4.8 | 99.52 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XI, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/07750 | Retrofitting | Providing 110 nos Functional Household Tap Connection (FHTC) to the households at Uttar Goler Gheri, Mouza-Jagannath Chak in Nandakumarpur Zone-II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/000348/2020-2021 | 391/RSD | 27/10/2020 | 26/11/2020 | M/S. JHARNA ENTERPRISE | 4.74 | 4.63 | 97.64 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XI, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/07750 | Retrofitting | Functional Household Tap Connection (FHTC) to the households at Purba Goler Gheri, Mouza-Jagannath Chak in Nandakumarpur Zone-II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E.Dte. (Part -II) | Assistant Engineer, Raidighi sub division |  | ORD/000360/2020-2021 | 427/RSD | 23/11/2020 | 22/01/2021 | M/S. JHARNA ENTERPRISE | 4.64 | 4.6 | 99.17 | 0
13 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XI, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/07750 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000652/2023-2024 | 255/AD | 15/01/2024 | 15/01/2024 | Resource Division | 11.25 | 0 | 0 | 0
Total | [13 empty] | 66.01 | 23.44 | 35.52