## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/07752 | Retrofitting | Extension of pipeline to provide Functional Household Tap Connection (FHTC) and construction of sluice valve chamber at Nandakumarpur Zone - III (Zone-XII of Mathurapur - II Block) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/000220/2022-2023 | 3061/AD | 13/07/2022 | 12/08/2022 | UNITED BUILDERS | 13.1 | 12.76 | 97.39 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/07752 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000082/2022-2023 | 5553/AD | 29/09/2022 | 29/09/2022 | Resource Division | 4.08 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/07752 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Nandakumarpur (Zone-III) Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Raidighi sub division |  | ORD/001336/2020-2021 | 2220/AD | 08/10/2020 | 08/10/2021 | UNITED BUILDERS | 108.61 | 72.25 | 66.52 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/07752 | Retrofitting | Laying distribution system of piped water supply and allied works at Zone- XII of Mathurapur -II Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000116/2023-2024 | 485/AD | 10/05/2023 | 09/06/2023 | KAMALA ENTERPRISE (I) | 8.57 | 6.63 | 77.34 | 80
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/07752 | Retrofitting | DISMANTLING AND RESTORATION OF CONCRETE VILLAGE ROAD FOR LDS WORK AT ZONE-I OF MATHURAPUR-I BLOCK FOR MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA MATHURAPUR UNDER RAIDIGHI SUB DIVISION OF ALIPORE DIVISION, PHE Dte. |  |  | BILL/00985/2024-2025 | BP-2024-25-472 | 17/08/2024 | 17/08/2024 | M/S RAJU CONSTRUCTION | 1.47 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/07752 | Retrofitting | Bill for way leave/ track crossing proposal with application ID : ER-SHAH-2023-WL-79 in IR/RBCS |  |  | BILL/00436/2024-2025 | BP-2024-25-163 | 04/06/2024 | 04/06/2024 | EASTERN RAILWAY (SEALDAH DIVISION) | 5.77 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/07752 | Retrofitting | Wayleave Facility Charges for crossing of pipeline near Nischintapur Halt railway station in Kulpi |  |  | BILL/01272/2025-2026 |  | 06/11/2025 | 06/11/2025 | EASTERN RAILWAY (SEALDAH DIVISION) | 5.16 | 0 | 0 | 0
Total | [13 empty] | 146.76 | 91.64 | 62.44