## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mrityunjoynagar W/S Scheme | SM/07754 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Sumanta Para & Kaylapara (Part) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001761/2020-2021 | 1220/KSD | 23/02/2021 | 05/03/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.82 | 7.51 | 196.58 | 99
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mrityunjoynagar W/S Scheme | SM/07754 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Purb Para for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001908/2020-2021 | 1323/KSD | 23/02/2021 | 05/03/2021 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 4.77 | 4.37 | 91.61 | 94
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mrityunjoynagar W/S Scheme | SM/07754 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dakhin Para (Phase-I) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001763/2020-2021 | 1222/KSD | 23/02/2021 | 05/03/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.1 | 3.74 | 91.32 | 94
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mrityunjoynagar W/S Scheme | SM/07754 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Sk. More for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001894/2020-2021 | 1316/KSD | 23/02/2021 | 05/03/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.6 | 3.25 | 90.43 | 94
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mrityunjoynagar W/S Scheme | SM/07754 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mondal Para (Phase-III) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001918/2020-2021 | 1328/KSD | 23/02/2021 | 05/03/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.76 | 3.46 | 91.83 | 94
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mrityunjoynagar W/S Scheme | SM/07754 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mrityunjoy Nagar (Phase-III) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001923/2020-2021 | 1334/KSD | 23/02/2021 | 05/03/2021 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 3.65 | 3.3 | 90.3 | 94
7 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mrityunjoynagar W/S Scheme | SM/07754 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Uttar Para (Part) & Purb Para (Part) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001790/2020-2021 | 1235/KSD | 23/02/2021 | 05/03/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.5 | 4.09 | 91.02 | 94
8 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mrityunjoynagar W/S Scheme | SM/07754 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Bark Para & Maity Para (Part) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001742/2020-2021 | 1215/KSD | 23/02/2021 | 05/03/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.71 | 3.4 | 91.6 | 94
9 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mrityunjoynagar W/S Scheme | SM/07754 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mondal Para (Phase-I) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001758/2020-2021 | 1217/KSD | 23/02/2021 | 05/03/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.76 | 7.32 | 194.41 | 98
10 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mrityunjoynagar W/S Scheme | SM/07754 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mrityunjoy Nagar (Phase-I) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001731/2020-2021 | 1213/KSD | 23/02/2021 | 05/03/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.65 | 3.27 | 89.44 | 94
11 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mrityunjoynagar W/S Scheme | SM/07754 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Kaylapara (Part - A) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001813/2020-2021 | 1252/KSD | 23/02/2021 | 05/03/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.78 | 9.23 | 193.35 | 94
12 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mrityunjoynagar W/S Scheme | SM/07754 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Uttar Para for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001842/2020-2021 | 1273/KSD | 23/02/2021 | 05/03/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.77 | 4.38 | 91.69 | 94
13 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mrityunjoynagar W/S Scheme | SM/07754 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mondal Para (Phase-II) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001845/2020-2021 | 1276/KSD | 23/02/2021 | 05/03/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.76 | 3.7 | 98.25 | 99
14 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mrityunjoynagar W/S Scheme | SM/07754 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dakhin Para (Phase-II) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001848/2020-2021 | 1279/KSD | 23/02/2021 | 05/03/2021 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 4.11 | 3.76 | 91.43 | 94
15 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mrityunjoynagar W/S Scheme | SM/07754 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Kaylapara (Part - C) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001915/2020-2021 | 1325/KSD | 23/02/2021 | 05/03/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.78 | 9.32 | 195.23 | 94
16 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mrityunjoynagar W/S Scheme | SM/07754 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Maity Para (Part) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001840/2020-2021 | 1271/KSD | 23/02/2021 | 05/03/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.93 | 7.69 | 195.52 | 94
17 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mrityunjoynagar W/S Scheme | SM/07754 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mrityunjoy Nagar (Phase-II) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001856/2020-2021 | 1287/KSD | 23/02/2021 | 05/03/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.65 | 3.31 | 90.71 | 94
18 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mrityunjoynagar W/S Scheme | SM/07754 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Kaylapara (Part - B) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001837/2020-2021 | 1268/KSD | 23/02/2021 | 05/03/2021 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 4.77 | 9.29 | 194.79 | 97
19 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mrityunjoynagar W/S Scheme | SM/07754 | Retrofitting | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works and Construction of 01 no. Pump House for Augmentation of Mrityunjoynagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000626/2022-2023 | 5979/AD | 20/10/2022 | 18/01/2023 | M/S. JAYDEEP DASGUPTA | 129.4 | 5 | 3.86 | 100
20 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mrityunjoynagar W/S Scheme | SM/07754 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000715/2023-2024 | 485/AD | 24/01/2024 | 24/01/2024 | Resource Division | 8.73 | 0 | 0 | 0
21 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mrityunjoynagar W/S Scheme | SM/07754 | Retrofitting | Construction of Household Tap Platform etc. at different household for Augmentation of Mrityunjaynagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub -Division of Alipore Division, P.H.E. Dte. (Part-B) (SM/11698) (SM/07754) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000549/2024-2025 | 3778/AD | 18/09/2024 | 18/10/2024 | M/S. JAYDEEP DASGUPTA | 7.27 | 0 | 0 | 100
Total | [13 empty] | 219.28 | 99.39 | 45.33