## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-IX, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/07755 | Retrofitting | Additional work (horizontal boring, village road crossing etc.) in connection with Functional Household Tap Connection (FHTCs) at Uttar Laxminarayanpur water supply scheme (Zone-IX of Mathurapur - I Block) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001548/2021-2022 | 714/RSD | 02/03/2022 | 01/05/2022 | M/S B.M. CONSTRUCTION | 4 | 2.96 | 74.12 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-IX, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/07755 | Retrofitting | Extension of pipeline to provide Functional Household Tap Connection (FHTC) (in between NP- 148-149-150, ext from 150,144-147,152-153-154, ext from 154-156,ext of 15-16, ext from 144-147,136-138,3-4-6,113-114-115,154-156-157, ext 36-37,ext from34-35,34-36,34-32-33,ext from 35) under Uttar Laxminarayanpur water supply scheme under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001546/2021-2022 | 712/RSD | 02/03/2022 | 01/05/2022 | M/S B.M. CONSTRUCTION | 4.7 | 4.7 | 99.92 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-IX, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/07755 | Retrofitting | Extension of pipeline to provide Functional Household Tap Connection (FHTC) (in between NP-44-45, 43-40, 35-36, ext from 57, 63-65, 64-63, 60-61, 45-53, ext from 50-52, 46-47, 45-53, 60-61, 52-53, etc) under Uttar Laxminarayanpur water supply scheme under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001769/2021-2022 | 627/RSD | 29/12/2021 | 13/01/2022 | M/S B.M. CONSTRUCTION | 4.28 | 4.26 | 99.56 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-IX, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/07755 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Uttar Lakshminarayanpur Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001310/2020-2021 | 2221/AD | 08/10/2020 | 07/10/2025 | M/S B.M. CONSTRUCTION | 106 | 43.49 | 41.03 | 90
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-IX, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/07755 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000642/2023-2024 | 246/AD | 15/01/2024 | 15/01/2024 | Resource Division | 12.88 | 0 | 0 | 0
Total | [13 empty] | 131.86 | 55.41 | 42.02