## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chemaguri W/S Scheme including | SM/07757 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000341/2023-2024 | 3156/AD | 29/09/2023 | 29/09/2023 | Resource Division | 0.3 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chemaguri W/S Scheme including | SM/07757 | Retrofitting | Making and fixing of permanent display board at headwork site of Chemaguri, Purusottampur, Mandirtala PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002177/2023-2024 | 955/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.61 | 0.2 | 33.33 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chemaguri W/S Scheme including | SM/07757 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000714/2023-2024 | 484/AD | 24/01/2024 | 24/01/2024 | Resource Division | 8.91 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chemaguri W/S Scheme including | SM/07757 | Retrofitting | Construction of Household Tap Platform at different household, Construction of Sluice Valve Chamder etc. for Chemaguri W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/07757) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000339/2024-2025 | 2771/AD | 28/06/2024 | 07/02/2025 | M. MUKHERJEE | 118.51 | 0 | 0 | 2
Total | [13 empty] | 128.33 | 0.2 | 0.16