## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 13 (thirteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Gangadharpur W/S | SM/07761 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Uttraabad Manasatala (Phase-II) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001823/2020-2021 | 1257/KSD | 23/02/2021 | 05/03/2021 | M/S. J.K. TRIPATHI & SONS | 4.61 | 4.27 | 92.59 | 93
2 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 13 (thirteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Gangadharpur W/S | SM/07761 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Kasarir Chak for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001793/2020-2021 | 1238/KSD | 23/02/2021 | 05/03/2021 | M/S. NIRMAL KUMAR MONDAL | 4.61 | 4.26 | 92.49 | 93
3 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 13 (thirteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Gangadharpur W/S | SM/07761 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Taltukuri for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001786/2020-2021 | 1231/KSD | 23/02/2021 | 05/03/2021 | KHATEJA CONSTRUCTION | 4.39 | 3.82 | 87.15 | 88
4 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 13 (thirteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Gangadharpur W/S | SM/07761 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Durganagar (Phase-II) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001833/2020-2021 | 1264/KSD | 23/02/2021 | 05/03/2021 | TIYASHA ENTERPRISE | 4.61 | 4.5 | 97.74 | 98
5 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 13 (thirteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Gangadharpur W/S | SM/07761 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Bahirchak (Phase-II) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001836/2020-2021 | 1267/KSD | 23/02/2021 | 05/03/2021 | L.N. ENTERPRISE | 2.63 | 2.46 | 93.36 | 94
6 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 13 (thirteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Gangadharpur W/S | SM/07761 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Uttraabad Manasatala (Phase-I) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001799/2020-2021 | 1241/KSD | 23/02/2021 | 05/03/2021 | M/S. J.K. TRIPATHI & SONS | 4.74 | 4.69 | 98.94 | 99
7 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 13 (thirteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Gangadharpur W/S | SM/07761 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Matilal (Phase-I) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001784/2020-2021 | 1229/KSD | 23/02/2021 | 05/03/2021 | M/S JANA CONSTRUCTION | 4.39 | 4.38 | 99.79 | 100
8 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 13 (thirteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Gangadharpur W/S | SM/07761 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Durganagar (Phase-I) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001806/2020-2021 | 1244/KSD | 23/02/2021 | 05/03/2021 | TIYASHA ENTERPRISE | 4.74 | 4.73 | 99.96 | 100
9 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 13 (thirteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Gangadharpur W/S | SM/07761 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Bahirchak (Phase-I) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001814/2020-2021 | 1253/KSD | 23/02/2021 | 05/03/2021 | L.N. ENTERPRISE | 3.95 | 3.95 | 99.9 | 100
10 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 13 (thirteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Gangadharpur W/S | SM/07761 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Paik Para (Phase-I) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001800/2020-2021 | 1242/KSD | 23/02/2021 | 05/03/2021 | TIYASHA ENTERPRISE | 4.74 | 4.73 | 99.78 | 100
11 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 13 (thirteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Gangadharpur W/S | SM/07761 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Matilal (Phase-II) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001826/2020-2021 | 1260/KSD | 23/02/2021 | 05/03/2021 | M/S JANA CONSTRUCTION | 3.51 | 3.5 | 99.73 | 100
12 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 13 (thirteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Gangadharpur W/S | SM/07761 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dhutkhali for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001788/2020-2021 | 1233/KSD | 23/02/2021 | 05/03/2021 | GROWING CONCERN | 4.4 | 4.39 | 99.93 | 100
13 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 13 (thirteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Gangadharpur W/S | SM/07761 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Paik Para (Phase-III) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001867/2020-2021 | 1298/KSD | 23/02/2021 | 05/03/2021 | TIYASHA ENTERPRISE | 3.29 | 0 | 0 | 80
14 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 13 (thirteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Gangadharpur W/S | SM/07761 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Uttraabad Manasatala (Phase-III) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001865/2020-2021 | 1296/KSD | 23/02/2021 | 05/03/2021 | TIYASHA ENTERPRISE | 4.39 | 4.38 | 99.9 | 100
15 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 13 (thirteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Gangadharpur W/S | SM/07761 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Paik Para (Phase-V) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001869/2020-2021 | 1300/KSD | 23/02/2021 | 05/03/2021 | MITRA CONSTRUCTION | 3.07 | 2.97 | 96.7 | 97
16 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 13 (thirteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Gangadharpur W/S | SM/07761 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Paik Para (Phase-IV) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001875/2020-2021 | 1304/KSD | 23/02/2021 | 05/03/2021 | MITRA CONSTRUCTION | 3.51 | 3.41 | 97.28 | 98
17 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 13 (thirteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Gangadharpur W/S | SM/07761 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Durganagar (Phase-IV) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001885/2020-2021 | 1307/KSD | 23/02/2021 | 05/03/2021 | GROWING CONCERN | 3.07 | 3.07 | 99.92 | 100
18 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 13 (thirteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Gangadharpur W/S | SM/07761 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Uttraabad Manasatala (Phase-IV) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001861/2020-2021 | 1292/KSD | 23/02/2021 | 05/03/2021 | KRISHNA CONSTRUCTION | 4.74 | 4.47 | 94.33 | 95
19 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 13 (thirteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Gangadharpur W/S | SM/07761 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Matilal (Phase-III) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001864/2020-2021 | 1295/KSD | 23/02/2021 | 05/03/2021 | M/S JANA CONSTRUCTION | 2.19 | 2.09 | 95.49 | 96
20 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 13 (thirteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Gangadharpur W/S | SM/07761 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Durganagar (Phase-III) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001877/2020-2021 | 1305/KSD | 23/02/2021 | 05/03/2021 | ANANTA KUMAR GIRI | 4.39 | 4.31 | 98.09 | 99
21 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 13 (thirteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Gangadharpur W/S | SM/07761 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Matilal (Phase-IV) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000162/2021-2022 | 405/KSD | 07/07/2021 | 22/07/2021 | M/S PIRBABA ENTERPRISE | 4.79 | 4.61 | 96.26 | 97
22 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 13 (thirteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Gangadharpur W/S | SM/07761 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Abad Gangadharpur (Part) and Bahirchak (Part) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000139/2021-2022 | 394/KSD | 07/07/2021 | 22/07/2021 | M/S BHAGABATI ENTERPRISE | 4.48 | 4.45 | 99.42 | 100
23 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 13 (thirteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Gangadharpur W/S | SM/07761 | Retrofitting | Laying of UPVC pipe line by replacing the damaged pipe line of different dia. for providing FHTC at Dakshin Gangadharpur Water Supply Scheme, Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000469/2021-2022 | 2417/AD | 15/09/2021 | 14/11/2021 | L.N. ENTERPRISE | 37.12 | 36.88 | 99.37 | 100
24 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 13 (thirteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Gangadharpur W/S | SM/07761 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households of different habitation for Dakshin Gangadharpur Water Supply Scheme, Block - Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Part-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000006/2022-2023 | 123/AD | 07/04/2022 | 22/04/2022 | FIDERE MARINE SERVICES PVT. LTD. | 12.99 | 7.25 | 55.82 | 80
25 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 13 (thirteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Gangadharpur W/S | SM/07761 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households of different habitation for Dakshin Gangadharpur Water Supply scheme, Block - Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Part-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000005/2022-2023 | 122/AD | 07/04/2022 | 22/04/2022 | FIDERE MARINE SERVICES PVT. LTD. | 12.98 | 12.97 | 99.92 | 100
26 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 13 (thirteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Gangadharpur W/S | SM/07761 | Retrofitting | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site of Dakshin Gangadharpur Water Supply Scheme, Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000019/2020-2021 | 2342/AD | 14/10/2020 | 13/12/2020 | M/S. MA BHABANI CONSTRUCTION | 10.26 | 10.24 | 99.85 | 100
27 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 13 (thirteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Gangadharpur W/S | SM/07761 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Paik Para (Phase-II) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001830/2020-2021 | 1261/KSD | 23/02/2021 | 05/03/2021 | TIYASHA ENTERPRISE | 4.6 | 4.53 | 98.33 | 0
28 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 13 (thirteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Gangadharpur W/S | SM/07761 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Gangadharpur for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001785/2020-2021 | 1230/KSD | 23/02/2021 | 05/03/2021 | SRI DURGA ENTERPRISE | 4.39 | 3.81 | 86.91 | 95
29 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 13 (thirteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Gangadharpur W/S | SM/07761 | Retrofitting | Continuation work order for the work of Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Executive Engineer, Alipore Division, PHE Dte. for the period from 01.01.2024 to 30.06.2024. | Assistant Engineer,HQ-II | Junior Engineer-1 | ORD/002122/2023-2024 | 5112/AD | 29/12/2023 | 26/06/2024 | M/S P. B. CONSTRUCTION | 2.4 | 0.8 | 33.29 | 30
30 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 13 (thirteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Gangadharpur W/S | SM/07761 | Retrofitting | Vehicle bill for month of APR-NOV23 |  |  | BILL/00437/2024-2025 | null | 28/05/2024 |  | RAJKUMAR MANNA | 18.72 | 0 | 0 | 0
31 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 13 (thirteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Gangadharpur W/S | SM/07761 | Retrofitting | Vehicle bill for month of APR-NOV23 |  |  | BILL/03542/2023-2024 | BP-2023-24-1273 | 27/03/2024 |  | RAJKUMAR MANNA | 18.72 | 0 | 0 | 0
32 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 13 (thirteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Gangadharpur W/S | SM/07761 | Retrofitting | HIRE bill for month of APR-NOV23 |  |  | BILL/03543/2023-2024 | BP-2023-24-1274 | 27/03/2024 |  | RAJKUMAR MANNA | 1.46 | 0 | 0 | 0
33 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 13 (thirteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Gangadharpur W/S | SM/07761 | Retrofitting | LAUNCH HIRE CHARGES FOR SEPT'22-OCT'22 UNDER KAKDWIP SUB-DIVISION, PHE DTE-FUEL |  |  | BILL/00682/2024-2025 | BP-2024-25-227 | 20/06/2024 |  | RAJKUMAR MANNA | 0.73 | 0 | 0 | 0
34 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 13 (thirteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Gangadharpur W/S | SM/07761 | Retrofitting | LAUNCH HIRE CHARGES FOR SEPT'22-OCT'22 UNDER KAKDWIP SUB-DIVISION, PHE DTE-FUEL |  |  | BILL/00682/2024-2025 | BP-2024-25-227 | 20/06/2024 |  | RAJKUMAR MANNA | 0.73 | 0 | 0 | 0
Total | [13 empty] | 214.3 | 159.94 | 74.63