## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bijoynagar Water Supp | SM/07762 | Retrofitting | Relaying and extension of pipeline due to FHTC work at Bijoynagar Water Supply Scheme Block- Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001064/2021-2022 | 5299/AD | 04/01/2022 | 05/03/2022 | ANUP PAUL | 28.3 | 28.2 | 99.64 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bijoynagar Water Supp | SM/07762 | Retrofitting | Additional laying of pipe line at Bijoynagar Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000084/2022-2023 | 1131/AD | 26/05/2022 | 25/06/2022 | M/S. BISWAS CONSTRUCTION(I) | 18.18 | 16.42 | 90.34 | 91
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bijoynagar Water Supp | SM/07762 | Retrofitting | Laying of pipeline of uncovered FHTC work area of Bijoynagar Water Supply Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001178/2022-2023 | 8773/AD | 21/12/2022 | 20/01/2023 | MONDAL ENTERPRISE - 2 (SDK) | 21.86 | 21.85 | 99.96 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bijoynagar Water Supp | SM/07762 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Bijoynagar Water Supply Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Canning sub division |  | ORD/000083/2020-2021 | 5306/AD | 18/02/2021 | 18/02/2022 | SPA ENTERPRISE | 281.51 | 193.37 | 68.69 | 85
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bijoynagar Water Supp | SM/07762 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households of Bijoynagar Water Supply Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division |  | ORD/001770/2020-2021 | 1456/CSD | 27/01/2021 | 13/03/2021 | SUSHANTA MANDAL | 1.26 | 2.51 | 199.49 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bijoynagar Water Supp | SM/07762 | Retrofitting | Construction of boundary wall at Pump House No. - 6 at Bijoynagar Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000023/2025-2026 | 2009/AD | 28/04/2025 | 28/05/2025 | RAHIMA ENTERPRISE | 11.49 | 0 | 0 | 0
Total | [13 empty] | 362.6 | 262.36 | 72.35