## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lahiripur Water Supply Sc | SM/07763 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Paschim Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - III) | Assistant Engineer, Canning sub division |  | ORD/001688/2020-2021 | 1387/CSD | 18/01/2021 | 04/03/2021 | A.P. CONSTRUCTION | 3.41 | 0 | 0 | 95
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lahiripur Water Supply Sc | SM/07763 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Ch Uttar Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - I) | Assistant Engineer, Canning sub division |  | ORD/001668/2020-2021 | 1370/CSD | 08/01/2021 | 22/02/2021 | FIDERE MARINE SERVICES PVT. LTD. | 3.29 | 0 | 0 | 95
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lahiripur Water Supply Sc | SM/07763 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at L Pur Majher Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - I) | Assistant Engineer, Canning sub division |  | ORD/001675/2020-2021 | 1375/CSD | 08/01/2021 | 22/02/2021 | ADITYA ENTERPRISE | 2.71 | 0 | 0 | 95
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lahiripur Water Supply Sc | SM/07763 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at L Pur Purba Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - I) | Assistant Engineer, Canning sub division |  | ORD/001676/2020-2021 | 1377/CSD | 08/01/2021 | 22/02/2021 | S.P. CONSTRUCTION (I) | 3.25 | 0 | 0 | 95
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lahiripur Water Supply Sc | SM/07763 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at L Pur Purba Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - II) | Assistant Engineer, Canning sub division |  | ORD/001678/2020-2021 | 1378/CSD | 08/01/2021 | 22/02/2021 | C.S. CONSTRUCTION | 2.4 | 0 | 0 | 95
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lahiripur Water Supply Sc | SM/07763 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Lahiripur of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - II) | Assistant Engineer, Canning sub division |  | ORD/001683/2020-2021 | 1380/CSD | 08/01/2021 | 22/02/2021 | M. CHAKRABORTY | 4.47 | 0 | 0 | 95
7 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lahiripur Water Supply Sc | SM/07763 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Lahiripur of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - III) | Assistant Engineer, Canning sub division |  | ORD/001684/2020-2021 | 1381/CSD | 08/01/2021 | 22/02/2021 | MODERN CONSTRUCTION | 4.47 | 0 | 0 | 95
8 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lahiripur Water Supply Sc | SM/07763 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Paschim Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - I) | Assistant Engineer, Canning sub division |  | ORD/001686/2020-2021 | 1383/CSD | 08/01/2021 | 22/02/2021 | KAYAL ENTERPRISE | 3.47 | 0 | 0 | 95
9 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lahiripur Water Supply Sc | SM/07763 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Paschim Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - II) | Assistant Engineer, Canning sub division |  | ORD/001687/2020-2021 | 1384/CSD | 08/01/2021 | 22/02/2021 | S.P. CONSTRUCTION (I) | 3.48 | 0 | 0 | 95
10 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lahiripur Water Supply Sc | SM/07763 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Santigachi of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - I) | Assistant Engineer, Canning sub division |  | ORD/001689/2020-2021 | 1388/CSD | 18/01/2021 | 04/03/2021 | M. CHAKRABORTY | 4.01 | 0 | 0 | 95
11 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lahiripur Water Supply Sc | SM/07763 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at L Pur Majher Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - II) | Assistant Engineer, Canning sub division |  | ORD/002040/2020-2021 | 1376/CSD | 08/01/2021 | 22/02/2021 | SANTANU GHOSH | 2.94 | 0 | 0 | 95
12 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lahiripur Water Supply Sc | SM/07763 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Ch Uttar Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - II) | Assistant Engineer, Canning sub division |  | ORD/001671/2020-2021 | 1371/CSD | 08/01/2021 | 22/02/2021 | S.C. ENTERPRISE (I) | 3.28 | 0 | 0 | 95
13 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lahiripur Water Supply Sc | SM/07763 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Lahiripur of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - IV) | Assistant Engineer, Canning sub division |  | ORD/001685/2020-2021 | 1382/CSD | 08/01/2021 | 22/02/2021 | SUKANTA HALDER | 4.42 | 0 | 0 | 95
14 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lahiripur Water Supply Sc | SM/07763 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Santigachi of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - II) | Assistant Engineer, Canning sub division |  | ORD/001690/2020-2021 | 1389/CSD | 18/01/2021 | 04/03/2021 | SHREEMAA ENTERPRISE | 4 | 0 | 0 | 95
15 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lahiripur Water Supply Sc | SM/07763 | Retrofitting | Trial run of CI/DI/AC/UPVC Rising Main & Distribution System at Lahiripur W/S Scheme under Canning Sub Division of Alipore Division, PHE Dte. [60 Days] | Assistant Engineer, Canning sub division |  | ORD/001768/2020-2021 | 1455/CSD | 27/01/2021 | 28/03/2021 | GANGA TUBEWELL AND HARDWARE | 1.27 | 0 | 0 | 98
16 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lahiripur Water Supply Sc | SM/07763 | Retrofitting | Extension of pipe line for FHTC work at Santigachhi of Lahiripur W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/001645/2021-2022 | 1513/CSD | 15/02/2022 | 07/03/2022 | C.S. CONSTRUCTION | 2.33 | 0 | 0 | 100
17 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lahiripur Water Supply Sc | SM/07763 | Retrofitting | Relaying pipe line for uncovered FHTC work at Lahiripur W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/001646/2021-2022 | 1514/CSD | 15/02/2022 | 17/03/2022 | S.P. CONSTRUCTION (I) | 3.24 | 0 | 0 | 95
18 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lahiripur Water Supply Sc | SM/07763 | Retrofitting | DI Pipeline protection of Lahiripur W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001635/2021-2022 | 1503/CSD | 15/02/2022 | 07/03/2022 | GANGA TUBEWELL AND HARDWARE | 1.83 | 0 | 0 | 98
19 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lahiripur Water Supply Sc | SM/07763 | Retrofitting | Trial run of CI/DI/AC/UPVC Rising Main & Distribution System at Lahiripur W/S Scheme under Canning Sub Division of Alipore Division, PHE Dte. [60 Days] | Assistant Engineer, Canning sub division |  | ORD/000001/2022-2023 | 01/CSD | 01/04/2022 | 31/05/2022 | GANGA TUBEWELL AND HARDWARE | 1.27 | 0 | 0 | 95
20 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lahiripur Water Supply Sc | SM/07763 | Retrofitting | Relaying of pipe line at node point 194-200, 217-209, 207-208 etc. at Lahiripur W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000289/2022-2023 | 299/CSD | 23/05/2022 | 22/06/2022 | S.P. CONSTRUCTION (I) | 3.61 | 0 | 0 | 90
21 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lahiripur Water Supply Sc | SM/07763 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Ch Majher Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - I) | Assistant Engineer, Canning sub division |  | ORD/001666/2020-2021 | 1368/CSD | 08/01/2021 | 22/02/2021 | GANGA TUBEWELL AND HARDWARE | 4.29 | 0 | 0 | 95
22 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lahiripur Water Supply Sc | SM/07763 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Lahiripur of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - I) | Assistant Engineer, Canning sub division |  | ORD/001682/2020-2021 | 1379/CSD | 08/01/2021 | 22/02/2021 | GANGA TUBEWELL AND HARDWARE | 4.47 | 0 | 0 | 95
23 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lahiripur Water Supply Sc | SM/07763 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Chargheri Dakhin Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - I) | Assistant Engineer, Canning sub division |  | ORD/001672/2020-2021 | 1372/CSD | 08/01/2021 | 22/02/2021 | SURYA ENTERPRISE | 4.66 | 0 | 0 | 95
24 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lahiripur Water Supply Sc | SM/07763 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Ch Bidhan Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - II) | Assistant Engineer, Canning sub division |  | ORD/001665/2020-2021 | 1367/CSD | 08/01/2021 | 22/02/2021 | SURYA ENTERPRISE | 3.6 | 0 | 0 | 95
25 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lahiripur Water Supply Sc | SM/07763 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Chargheri Dakhin Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - III) | Assistant Engineer, Canning sub division |  | ORD/001674/2020-2021 | 1374/CSD | 08/01/2021 | 22/02/2021 | SURYA ENTERPRISE | 4.74 | 0 | 0 | 95
26 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lahiripur Water Supply Sc | SM/07763 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Santigachi of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - IV) | Assistant Engineer, Canning sub division |  | ORD/001692/2020-2021 | 1391/CSD | 18/01/2021 | 04/03/2021 | BENGAL BUILDERS | 3.98 | 0 | 0 | 95
27 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lahiripur Water Supply Sc | SM/07763 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Lahiripur W/S Scheme (uncovered area), Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000219/2023-2024 | 1024/AD | 13/06/2023 | 28/07/2023 | SUPRITI ENTERPRISE | 59.73 | 0 | 0 | 99
28 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lahiripur Water Supply Sc | SM/07763 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Chargheri Dakhin Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - II) | Assistant Engineer, Canning sub division |  | ORD/001673/2020-2021 | 1373/CSD | 08/01/2021 | 22/02/2021 | A.P. CONSTRUCTION | 4.71 | 0 | 0 | 95
29 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lahiripur Water Supply Sc | SM/07763 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Santigachi of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - III) | Assistant Engineer, Canning sub division |  | ORD/001691/2020-2021 | 1390/CSD | 18/01/2021 | 04/03/2021 | S.P. CONSTRUCTION (I) | 3.99 | 0 | 0 | 95
Total | [13 empty] | 157.31 | 0 | 0