## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone I Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathur | SM/08118 | Retrofitting | Laying distribution pipe line damaged due to widening and strengthening of Falta PWD main road at Falta Zone-I for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001192/2021-2022 | 5709/AD.. | 31/01/2022 | 01/04/2022 | S.P. CONSTRUCTION (V) | 50.97 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone I Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathur | SM/08118 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000020/2022-2023 | 1197/AD | 30/05/2022 | 30/05/2022 | Resource Division | 3.98 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone I Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathur | SM/08118 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Falta, Zone-I including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Diamond Harbour sub division |  | ORD/000076/2020-2021 | 5353/AD | 19/02/2021 | 19/02/2022 | M/S. S.S. ENTERPRISE | 440.86 | 152.32 | 34.55 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone I Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathur | SM/08118 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Paschim Surendranagar (Phase-II), for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001824/2020-2021 | 1258/KSD | 23/02/2021 | 05/03/2021 | M/S B. ENTERPRISE | 4.24 | 4.24 | 100 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone I Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathur | SM/08118 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mandirtala (Phase-II) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001825/2020-2021 | 1259/KSD | 23/02/2021 | 05/03/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.78 | 4.74 | 99.27 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone I Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathur | SM/08118 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Gosta Para (Phase-I), for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001765/2020-2021 | 1224/KSD | 23/02/2021 | 05/03/2021 | M/S B. ENTERPRISE | 4.25 | 4.25 | 100 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone I Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathur | SM/08118 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Chakfuldubi (Phase-V) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001888/2020-2021 | 1310/KSD | 23/02/2021 | 05/03/2021 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 4.77 | 2.85 | 59.72 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone I Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathur | SM/08118 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mandirtala (Phase-III) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001872/2020-2021 | 1302/KSD | 23/02/2021 | 05/03/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.78 | 4.75 | 99.39 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone I Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathur | SM/08118 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- 1 no. Block, for Paschim Surendranagar Zone - II W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001926/2020-2021 | 1338/KSD | 23/02/2021 | 05/03/2021 | M/S B. ENTERPRISE | 4.28 | 4.28 | 100 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone I Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathur | SM/08118 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mahendranagar (Paschim) (Phase-I), for Paschim Surendranagar Zone - II W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001787/2020-2021 | 1232/KSD | 23/02/2021 | 05/03/2021 | M/S B. ENTERPRISE | 4.27 | 4.27 | 100 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone I Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathur | SM/08118 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Chakfuldubi (Phase-II) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001831/2020-2021 | 1262/KSD | 23/02/2021 | 05/03/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.77 | 4.63 | 96.95 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone I Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathur | SM/08118 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Paschim Surendranagar (Phase-I), for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001832/2020-2021 | 1263/KSD | 23/02/2021 | 05/03/2021 | M/S B. ENTERPRISE | 4.24 | 4.24 | 100 | 0
13 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone I Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathur | SM/08118 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Bamankhali (Phase-II) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001834/2020-2021 | 1265/KSD | 23/02/2021 | 05/03/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.77 | 4.72 | 98.98 | 0
14 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone I Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathur | SM/08118 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Chakfuldubi (Part) & Bamankhali (Part) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001794/2020-2021 | 1239/KSD | 23/02/2021 | 05/03/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.66 | 4.6 | 98.73 | 0
15 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone I Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathur | SM/08118 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Kali Mandir Para, for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001779/2020-2021 | 1226/KSD | 23/02/2021 | 05/03/2021 | M/S B. ENTERPRISE | 4.25 | 4.25 | 100 | 0
16 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone I Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathur | SM/08118 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Bamankhali (Phase-I) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001812/2020-2021 | 1251/KSD | 23/02/2021 | 05/03/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.78 | 4.71 | 98.62 | 0
17 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone I Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathur | SM/08118 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Bamankhali (Phase-IV) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001890/2020-2021 | 1312/KSD | 23/02/2021 | 05/03/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.77 | 4.74 | 99.19 | 0
18 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone I Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathur | SM/08118 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Bamankhali (Phase-III) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001892/2020-2021 | 1314/KSD | 23/02/2021 | 05/03/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.78 | 4.72 | 98.83 | 0
19 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone I Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathur | SM/08118 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- 2 no. Block, for Paschim Surendranagar Zone - II W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001804/2020-2021 | 1243/KSD | 23/02/2021 | 05/03/2021 | M/S B. ENTERPRISE | 4.28 | 4.28 | 100 | 0
20 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone I Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathur | SM/08118 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Falta, Zone-VI including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Diamond Harbour sub division |  | ORD/000065/2021-2022 | 342/AD | 12/05/2021 | 12/05/2022 | BALAJEE ENTERPRISE. | 337.44 | 119.83 | 35.51 | 100
21 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone I Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathur | SM/08118 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Purba Para, for Paschim Surendranagar Zone - II W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001852/2020-2021 | 1283/KSD | 23/02/2021 | 05/03/2021 | M/S B. ENTERPRISE | 4.27 | 4.27 | 100 | 0
22 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone I Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathur | SM/08118 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mandirtala (Phase-IV) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001862/2020-2021 | 1293/KSD | 23/02/2021 | 05/03/2021 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 4.77 | 4.74 | 99.2 | 0
23 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone I Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathur | SM/08118 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mandirtala (Phase-I) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001809/2020-2021 | 1247/KSD | 23/02/2021 | 05/03/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.77 | 4.69 | 98.15 | 0
24 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone I Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathur | SM/08118 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Chakfuldubi (Phase-I) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001810/2020-2021 | 1249/KSD | 23/02/2021 | 05/03/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.77 | 4.75 | 99.46 | 0
25 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone I Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathur | SM/08118 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Chakfuldubi (Phase-IV) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001886/2020-2021 | 1308/KSD | 23/02/2021 | 05/03/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.5 | 3.39 | 75.4 | 0
26 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone I Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathur | SM/08118 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Chakfuldubi (Phase-III) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001866/2020-2021 | 1297/KSD | 23/02/2021 | 05/03/2021 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 4.77 | 4.73 | 99.12 | 0
Total | [13 empty] | 933.79 | 368.99 | 39.51