## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone V Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathur | SM/08122 | Retrofitting | Laying of distribution pipeline due to changing of alignment drawing as per site condition and restoration of distribution pipeline (damaged portion) due to widening of Irrigation canal along with road restoration at Zone-V of Falta Block of Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (2nd Call) | Assistant Engineer, Diamond Harbour sub division |  | ORD/001113/2022-2023 | 8776/AD | 21/12/2022 | 20/01/2023 | TIYASHA ENTERPRISE | 33.47 | 21.4 | 63.93 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone V Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathur | SM/08122 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000439/2023-2024 | 3621/AD | 30/10/2023 | 30/10/2023 | Resource Division | 19.73 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone V Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathur | SM/08122 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Falta, Zone-V including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Diamond Harbour sub division |  | ORD/000020/2021-2022 | 340/AD | 12/05/2021 | 12/05/2022 | CONCORD ENGINEERING | 309.32 | 315.77 | 102.08 | 90
Total | [13 empty] | 362.53 | 337.17 | 93.01