## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone III Diamond Harbour II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/08124 | Retrofitting | Hiring of an Inspection Vehicle (Diesel Operated) for the use of "Mega Surface Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas", under Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. for 4(four) months (period from 01/01/2022 to 30/04/2022) | Assistant Engineer, Diamond Harbour sub division |  | ORD/001207/2021-2022 | 404/DHSD | 28/12/2021 | 28/04/2022 | SUMAN HALDER | 1.6 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone III Diamond Harbour II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/08124 | Retrofitting | Laying distribution system in left out portion for 100% coverage of Functional Household Tap Connection (FHTC) at Gondia Raghunathpur village due to Swajal Gram activities under Zone-III of Diamond Harbour-II within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/000581/2022-2023 | 5857/AD | 18/10/2022 | 17/11/2022 | SRIJON ENTERPRISE | 38.07 | 0 | 0 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone III Diamond Harbour II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/08124 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000003/2021-2022 | 2022/AD | 01/09/2021 | 01/09/2021 | Resource Division | 4.07 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone III Diamond Harbour II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/08124 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000121/2022-2023 | 12051/AD | 27/02/2023 | 27/02/2023 | Resource Division | 4.82 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone III Diamond Harbour II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/08124 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Diamond Harbour-II, Zone-III including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Diamond Harbour-II under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. (Phase-I) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/000075/2020-2021 | 5352/AD | 19/02/2021 | 19/02/2022 | SUPRITI ENTERPRISE | 404.97 | 212.18 | 52.39 | 99
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone III Diamond Harbour II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/08124 | Retrofitting | Preparation of design, drawing for foundation for the proposed R.C.C. Over Head Reservoir at Zone-II (Akrapanji, OHR Size-1250) within Diamond Harbour-II Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/002092/2022-2023 | 326/DHSD | 07/11/2022 | 14/11/2022 | ASTER CONSULTANCY | 0.5 | 0 | 0 | 100
7 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone III Diamond Harbour II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/08124 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000920/2023-2024 | 1262/AD | 02/03/2024 | 02/03/2024 | Resource Division | 0.93 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone III Diamond Harbour II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/08124 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000881/2023-2024 | 755/AD | 03/02/2024 | 03/02/2024 | Resource Division | 28.59 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone III Diamond Harbour II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/08124 | Retrofitting | Balance works under the Augmentation scheme of Zone-IIIA at Diamond Harbour- II block for providing House Hold Tap connection, under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/001403/2024-2025 | 5527/AD | 28/12/2024 | 11/02/2025 | DURGA ENTERPRISE | 19.3 | 0 | 0 | 0
Total | [13 empty] | 502.85 | 212.18 | 42.2