## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 08 eight nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Achintyanagar WS Scheme including | SM/08628 | Retrofitting | Development of Land for sinking of tubewell at 4th Tubewell Site of Achintyanagar W/S scheme under JJM, Block : Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division | ORD/000430/2022-2023 | 203/KSD | 01/06/2022 | 08/06/2022 | M/S B. ENTERPRISE | 0.61 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 08 eight nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Achintyanagar WS Scheme including | SM/08628 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Achintyanagar Water Supply Scheme including one year Operation and Maintenance and repairing of distribution main, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000271/2021-2022 | 1718/AD | 17/08/2021 | 17/08/2022 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 251.54 | 0 | 0 | 70
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 08 eight nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Achintyanagar WS Scheme including | SM/08628 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000317/2023-2024 | 3126/AD | 29/09/2023 | 29/09/2023 | Resource Division | 0.3 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 08 eight nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Achintyanagar WS Scheme including | SM/08628 | Retrofitting | Supplying, fitting, fixing and delivery of different dia. specials for Achintyanagar W/S Scheme under JJM, Block- Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division | ORD/000999/2023-2024 | 506/KSD | 03/10/2023 | 10/10/2023 | M/S B. ENTERPRISE | 3.74 | 0 | 0 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 08 eight nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Achintyanagar WS Scheme including | SM/08628 | Retrofitting | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Achintyanagar W/S Scheme, Block - Pathar Pratima under JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/08628) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000162/2024-2025 | 2513/AD | 15/06/2024 | 15/07/2024 | SHREE J M CONSTRUCTION | 20.39 | 0 | 0 | 100
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 08 eight nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Achintyanagar WS Scheme including | SM/08628 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000780/2023-2024 | 614/AD | 29/01/2024 | 29/01/2024 | Resource Division | 12.28 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 08 eight nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Achintyanagar WS Scheme including | SM/08628 | Retrofitting | HIRE bill for month of MAY-JUL23 |  |  | BILL/03539/2023-2024 | BP-2023-24-1270 | 27/03/2024 | 27/03/2024 | RAJKUMAR MANNA | 4.56 | 0 | 0 | 0
Total | [13 empty] | 293.41 | 0 | 0