## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 43 forty three nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Sibnagar WS Scheme including | SM/08629 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households for 43 (forty three) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Sibnagar W/S Scheme including one year Operation & Maintenance and repairing of distribution main, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division | ORD/000015/2021-2022 | 3164/AD | 09/11/2021 | 09/11/2022 | M/S. SAMADDAR CONSTRUCTION | 84.8 | 73.16 | 86.28 | 80
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 43 forty three nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Sibnagar WS Scheme including | SM/08629 | Retrofitting | Surging of 01 no. Big dia Tubewell of Sibnagar W/S Scheme under JJM, Block - Kakdwip under Kakdwip Sub-Division under Alipore Division P.H.Engg. Dte. | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/000231/2023-2024 | 157/KSD | 01/06/2023 | 21/06/2023 | S.K.GOLUI | 1.37 | 1.37 | 100 | 95
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 43 forty three nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Sibnagar WS Scheme including | SM/08629 | Retrofitting | Making and fixing of permanent display board at headwork site of Gobindapur, Ramchandrapur, Ramchandranagar, Srikrishnanagar, Sibnagar, Manmathapur (Manmathanagar) PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002143/2023-2024 | 943/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.94 | 0 | 0 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 43 forty three nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Sibnagar WS Scheme including | SM/08629 | Retrofitting | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Shibnagar PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (SM/08629) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/003194/2023-2024 | 1281/KSD | 29/12/2023 | 03/01/2024 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 0 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 43 forty three nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Sibnagar WS Scheme including | SM/08629 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000840/2023-2024 | 688/AD | 30/01/2024 | 30/01/2024 | Resource Division | 11.37 | 0 | 0 | 0
Total | [13 empty] | 98.96 | 74.53 | 75.31