## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 12 twelve nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Sitarampur WS Scheme including on | SM/08630 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Sitarampur Water Supply Scheme including one year Operation & Maintenance and repairing of distribution system, Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000033/2022-2023 | 675/AD | 05/05/2022 | 02/09/2022 | GROWING CONCERN | 150.83 | 0 | 0 | 80
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 12 twelve nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Sitarampur WS Scheme including on | SM/08630 | Retrofitting | Supply, Delivery & Laying of Specials Required for Laying Rising Main and Inter-Connection Line between Tubewells and other allied works for providing FHTC under JJM at Sitarampur Water Supply Scheme, Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division PHE Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000224/2022-2023 | 3065/AD | 13/07/2022 | 12/08/2022 | ANANTA KUMAR GIRI | 7.64 | 0 | 0 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 12 twelve nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Sitarampur WS Scheme including on | SM/08630 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000781/2023-2024 | 615/AD | 29/01/2024 | 29/01/2024 | Resource Division | 12.81 | 0 | 0 | 0
Total | [13 empty] | 171.27 | 0 | 0