## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 12 twelve nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Bagdanga WS Scheme including one | SM/08631 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bagdanga Water Supply Scheme including one year Operation and Maintenance and repairing of distribution main, Block - Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000014/2021-2022 | 3163/AD | 09/11/2021 | 09/11/2022 | MAHAVIR PUMPS MANUFACTURING PVT. LTD | 90.17 | 0 | 0 | 26
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 12 twelve nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Bagdanga WS Scheme including one | SM/08631 | Retrofitting | Relaying of DI pipeline with ancillary pipeline protection work for crossing over pond (9 nos.) at Bagbagan of Gosaba W/S Scheme (Zone-II), Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000287/2023-2024 | 184/CSD | 22/05/2023 | 21/06/2023 | SUSHANTA MANDAL | 4.74 | 4.11 | 86.73 | 99
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 12 twelve nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Bagdanga WS Scheme including one | SM/08631 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000294/2023-2024 | 3061/AD | 28/09/2023 | 28/09/2023 | Resource Division | 0.3 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 12 twelve nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Bagdanga WS Scheme including one | SM/08631 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000800/2023-2024 | 645/AD | 30/01/2024 | 30/01/2024 | Resource Division | 10 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 12 twelve nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Bagdanga WS Scheme including one | SM/08631 | Retrofitting | Construction of Household Tap Platform at different households, Laying pipe line of different damaged portion in different node within the command area of Bagdanga PWSS, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/08631) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000649/2024-2025 | 4168/AD | 21/10/2024 | 19/01/2025 | ASHIS ENTERPRISE | 96.45 | 0 | 0 | 100
Total | [13 empty] | 201.66 | 4.11 | 2.04